## Sheet1
14/8/2016
Updated information received from Major Ports for Solar Rooftop
Sl | Port | Info. recd on | No of buildings | Names of building | Roof areas (sq mts) | Roof type given | Total kWp | RESCO or EPC | Remarks | Local contact person | email | Mobile | Landline
1 | Chennai | 2016-07-26 | 5 | Given | 4854 | Given | To be calculated | To find out | Full details given in SECI format | Mr P. Shanmuganathan, CME | cme@chennaiport.gov.in | 9443594006 | 044-25362070
2 | Cochin | 2016-07-19 | 6 | Given | 1490 | Yes | To be calculated |  | Roof sizes of each building is given | Mr S.K. Das, CME | cme@cochinport.gov.in | 9847049022 | 0484-2666639
3 | Haldia | 2016-07-20 | 9 | Given | 2731 | RCC | To be calculated |  | Apart from these buildings, Port has placed PO for 160 kW rooftop and which shall be comm. By Aug'16 | Shri Somnath Mukhopadhyay, Nodal Officer | somnath.haldock@gmail.com | 9434052332 | 03224-252483
4 | JNPT | 2016-07-22 | 12 | Given | 11160 | Not given | 411 |  | Out of 822 kW approx capacity possible, order for 411 kW has been placed & expected to be comm. In Aug'16 | Mr Arvind Pradhan, Nodal Officer | arvindpradhan@jnport.gov.in | 7045232389, 9820160457 | 022-27244196
5 | Kamarajar | 2016-07-25 | 4 | Sub-stn building, car parking yard, office buildings | 1788 | RCC |  |  | Roof area of each building to be given separately | Shri Sunder Moorthy, Nodal Officer | moorthy@epl.gov.in | 9600162167 | 044-27950018
6 | Kandla | 2016-07-22 | 1 | Admin block | 2100 | RCC | 175 |  | Tender issued for 175 kW on 28-6-16 and desire same to be included under MNRE subsidy scheme for Govt buidlings. No details of additional buildings given | Mr K.C. Kuncheria, CME | cmekpt@gmail.com | 9825226944 | 02836-270632
7 | Kolkata | 2016-07-29 | 2 | Given | 3125 | Not given |  |  | Planned release of NIT directly in Sep'16 for both buildings | Shri Somnath Mukhopadhyay, Nodal Officer and Mrs S. Pradhan (Secretary) | somnath.haldock@gmail.com | 9434052332 | 033-22303451
8 | Mangalore | 2016-07-19 | 4 | Given | NA | NA | 840 |  | Bid submission for 840 kW is on 2-8-16. Port informs that no other building is available for rooftop | Mr K. Aleshappaa, Nodal Officer | eee2@nmpt.in | 9880079309 | 0824-2407341, 2887399
9 | Mormugao | 2016-07-20 | Not given | Main Admin building & Hospital | 4300 | RCC | 240 |  | PO placed in May'16 for 240 kW and expected comm. In Oct'16. No details of additional buildings given | Mr A. Ganeshan, CME | cmemptgoa@hotmail.com | 9763397634 | 0832-2521170/ 71
10 | Mumbai | 2016-07-02 | 10 | Given | 6700 | Yes | To be calculated |  | Port has sent details to SECI for undertaking feasibility study | Mr A.B. Kulkarni, EE |  |  | 022-66565656/ 2377413
11 | Paradip | 0461-2352500 | 18 | Given | 30134 | Given | To be calculated |  |  | Shri Chandan Panigrahi, Nodal Officer and Mr P.P. Saha, EE | chandan.panigrahi@rediffmail.com, ppsahappt@gmail.com | 9937334222 | 06722-222168
12 | Vizag | 2016-07-22 | 88 | Given | 32155 | Given | 2256 |  | Actual capacity assessment to be done | Shri P Kamaraju, Nodal Officer | kamaraju_pandiri@yahoo.co.in | 9948298307 | 0891-2564787
13 | VOCPT | 2016-07-21 | Not given | Not given | 3732 | RCC | To be calculated |  | Apart from 3750 sq mts AC sheet roof is also available, but which cannot be used | Shri Baskar R, Nodal Officer | rbaskartpt@gmail.com | 9486983865 | 0461-2352500, 2372210
|  | Total |  |  | 104269
14 | Andaman Dock, Port Blair | 2016-07-07 | Given | Given | Given | Given | 560 |  | Feasibility study report attached for 560 kW | Chief Engineer | alhw@and.nic.in |  | 03192-232864, 232862, 232753

## Sheet2
2016-08-08
Updated information received from Major Ports for Solar Rooftop
Port
Chennai
Cochin
Haldia
JNPT
Kamarajar
Kandla
Kolkata
Mangalore
Mormugao
Mumbai
Paradip
Vizag
VOCPT
Andaman Dock, Port Blair