## Sheet1
Wind Projects being implemented under schemes operated by SECI
Sr. No. | Project ID | Name of Project Developer | Date of issuance of LOA | Project Capacity (MW) | Project Location (State) | Effective Date of PPA | Actual Commissioning Date/ Remarks | Total capacity commissioned as on date
1000 MW ISTS-connected Wind Power Projects (Tranche-I)
1 | WPD-ISTS-T1-MEIPL-P1-250TN | Mytrah Vayu (Sabarmati) Private Limited | 05.04.2017 | 250 | Thoothukkudi, Tamil Nadu | 21.07.2017 | 28.01.2019 (128.79 MW) 13.04.2019 (58.32) 09.05.2019 (62.89 MW) | 250
2 | WPD-ISTS-T1-GIWEL-P1-249.9TN | Green Infra Renewable Energy Limited | 05.04.2017 | 249.9 | Tuticorin, Tamil Nadu | 21.07.2017 | 07.10.2018 | 249.9
3 | WPD-ISTS-T1-IWISL-P2-50GJ | Wind One Renergy Private Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | 02.07.2019 | 50
4 | WPD-ISTS-T1-IWISL-P1-50GJ | Wind Two Renergy Private Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | 04.07.2019 | 50
5 | WPD-ISTS-T1-IWISL-P4-50GJ | Wind Three Renergy Private Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | 29.06.2019 | 50
6 | WPD-ISTS-T1-IWISL-P5-50GJ | Wind Four Renergy Private Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | - | 0
7 | WPD-ISTS-T1-IWISL-P3-50GJ | Wind Five Renergy Private Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | 04.07.2019 | 50
8 | WPD-ISTS-T1-OKWPL-P1-250GJ | Ostro Kutch Wind Private Limited | 05.04.2017 | 250 | Kutch, Gujarat | 21.07.2017 | 21.08.2018 (126 MW) 31.10.2018 (50 MW) 26.12.2018 (50 MW) 29.03.2019 (24 MW) | 250
9 | WPD-ISTS-T1-AGEMPL-P1-50GJ | Adani Green Energy (MP) Limited | 05.04.2017 | 50 | Kutch, Gujarat | 21.07.2017 | 20.10.2019 | 50
1000 MW ISTS-connected Wind Power Projects (Tranche-II)
1 | WPD-ISTS-T2-RPVPL-P1-250GJ | ReNew Power Private Limited | 03.11.2017 | 250 | Kutch, Gujarat | 02.01.2018 | 17.05.2019 (126 MW) 29.09.2019 (58.5) 01.09.2020 (27.6 MW) 06.02.2021 (18 MW) | 230.1
2 | WPD-ISTS-T2-OSWPPL-P1-200TN | Greenko Sironj Wind Power Pvt Ltd | 03.11.2017 | 200 | Tuticorin, Tamil Nadu | 19.12.2017 | 05.03.2019 (100 MW) 13.04.2019 (100 MW) | 200
3 | WPD-ISTS-T2-IWISL-P1-50GJ | Haroda Wind Energy Private Limited | 03.11.2017 | 50 | Kutch, Gujarat | 27.12.2017 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
4 | WPD-ISTS-T2-IWISL-P2-50GJ | Khatiyu Wind Energy Private Limited | 03.11.2017 | 50 | Kutch, Gujarat | 27.12.2017 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
5 | WPD-ISTS-T2-IWISL-P3-50GJ | Vigodi Wind Energy Private Limited | 03.11.2017 | 50 | Kutch, Gujarat | 27.12.2017 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
6 | WPD-ISTS-T2-IWISL-P4-50GJ | Nani Virani Wind Energy Private Limited | 03.11.2017 | 50 | Kutch, Gujarat | 27.12.2017 | 03.09.2021 (10 MW); 22.03.2022 (10 MW); 12.05.2022 (10 MW) | 30
7 | WPD-ISTS-T2-IWISL-P5-50GJ | Ravapar Wind Energy Private Limited | 03.11.2017 | 50 | Kutch, Gujarat | 27.12.2017 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
8 | WPD-ISTS-T2-GIWEL-P1-250MP | Green Infra Wind Energy Limited | 03.11.2017 | 250 | Kutch, Gujarat | 02.01.2018 | 23.06.2019 (126 MW) 20.10.2019 (54.6 MW) 03.01.2020 (50.4 MW) 06.02.2020 (19 MW) | 250
9 | WPD-ISTS-T2-AGEMPL-P1-50GJ | Adani Wind Energy Kutchh One Ltd | 03.11.2017 | 50 | Kutch, Gujarat | 29.12.2017 | 05.03.2020 | 50
2000 MW ISTS-connected Wind Power Projects (Tranche-III)
1 | WPD-ISTS-T3-RWEAP2PL-P1-100GJ | ReNew Wind Energy (AP2) Private Limited | 23.02.2018 | 100 | Kutch, Gujarat | 24.05.2018 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
2 | WPD-ISTS-T3-RWEAP2PL-P2-300GJ | ReNew Wind Energy (AP2) Private Limited | 23.02.2018 | 300 | Kutch, Gujarat | 24.05.2018 | 15.10.2020 (50 MW); 04.11.2020 (22.5 MW); 12.11.2020 (22.5 MW); 07.12.2020 (52.5MW); 17.12.2020 (22.5MW); 24.12.2020 (12.5MW); 29.12.2020 (10 MW); 22.01.2021 (50 MW); 08.02.2021 (12.5 MW); 12.02.2021 (10 MW); 18.02.2021 (10 MW); 01.03.2021 (10 MW); 05.03.2021 (10 MW); 11.03.2021 (5 MW) | 300
3 | WPD-ISTS-T3-GIWEL-P1-300GJ | Green Infra Wind Energy Limited | 23.02.2018 | 300 | Kutch, Gujarat | 24.05.2018 | 05.07.2019 (73.5 MW); 06.09.2019 (50.4 MW); 02.11.2019 (52.5 MW); 03.01.2020 (50.4 MW); 18.06.2020 (73.2 MW) | 300
4 | WPD-ISTS-T3-IWISL-P1-50GJ | ALIENTO WIND ENERGY PRIVATE LIMITED | 23.02.2018 | 50 | Kutch, Gujarat | 24.05.2018 | - | 0
5 | WPD-ISTS-T3-IWISL-P2-50GJ | FLURRY WIND ENERGY PRIVATE LIMITED | 23.02.2018 | 50 | Kutch, Gujarat | 24.05.2018 | - | 0
6 | WPD-ISTS-T3-IWISL-P3-50GJ | TEMPEST WIND ENERGY PRIVATE LIMITED | 23.02.2018 | 50 | Kutch, Gujarat | 24.05.2018 | - | 0
7 | WPD-ISTS-T3-IWISL-P4-50GJ | VUELTA ENERGY PRIVATE LIMITED | 23.02.2018 | 50 | Kutch, Gujarat | 24.05.2018 | - | 0
8 | WPD-ISTS-T3-TPL-P1-300.3GJ | Torrent Power Limited | 23.02.2018 | 300.3 | Kutch, Gujarat | 24.05.2018 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
9 | WPD-ISTS-T3-TPL-P2-199.5GJ | Torrent Power Limited | 23.02.2018 | 199.5 | Kutch, Gujarat | 24.05.2018 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
10 | WPD-ISTS-T3-AC-P1-300GJ | Alfanar Energy Private Limited | 23.02.2018 | 300 | Kutch, Gujarat | 24.05.2018 | 28.07.2020 (88 MW); 02.08.2020 (50.6 MW); 04.09.2020 (29.6 MW); 11.09.2020 (15.4 MW); 01.10.2020 (15.4 MW); 20.10.2020 (15.4 MW); 18.11.2020 (20.2 MW); 29.12.2020 (15.6 MW); 22.02.2021 (11.4 MW); 04.03.2021 (11 MW); 25.03.2021 (15.4 MW); 31.03.2021 (12 MW) | 300
11 | WPD-ISTS-T3-AGEMPL-P1-250GJ | Adani Green Energy (MP) Limited | 23.02.2018 | 250 | Kutch, Gujarat | 24.05.2018 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
12 | WPD-ISTS-T3-BWEPL-P1-50.2TN | Vivid Solaire Energy Private Limited | 23.02.2018 | 50.2 | Tuticorin, Tamil Nadu | 24.05.2018 | 24.11.2019 (50.2MW) | 50.2
2000 MW ISTS-connected Wind Power Projects (Tranche-IV)
1 | WPD-ISTS-T4-SESPL-P1-250GJ | Continuum Power Trading (TN) Pvt Ltd | 01.06.2018 | 250 | Kutch, Gujarat | 30.08.2018 | 11.04.2021 (32 MW); 21.04.2021 (18 MW); 12.08.2021 (10 MW); 06.10.2021 (10 MW); 14.04.2022 (18 MW) | 88
2 | WPD-ISTS-T4-SEPL-P1-300TN | Sprng Renewable Energy Private Limited | 01.06.2018 | 300 | Tiruppur and Karur, Tamil Nadu | 30.08.2018 | 27.03.2021 (60 MW); 31.03.2021 (93 MW); 04.07.2021 (39 MW); 13.07.2021 (36 MW); 20.08.2021 (12 MW); 04.09.2021 (15 MW); 13.10.2021 (12 MW); 22.10.2021 (12 MW); 30.10.2021 (21 MW) | 300
3 | WPD-ISTS-T4-BEPL-P1-285GJ | Avikiran Solar India Pvt Ltd. | 01.06.2018 | 285 | Kutch, Gujarat | 30.08.2018 | 23.02.2022 (16.8 MW); 03.03.2022 (25.2 MW); 05.03.2022 (35.7 MW); 10.03.2022 (21 MW); 18.04.2022 (12.6 MW); 21.04.2022 (14.7 MW); 15.06.2022 (25.2 MW); 18.08.2022 (14.7 MW) | 165.9
4 | WPD-ISTS-T4-BWEPL-P1-200TN | Vivid Solaire Energy Pvt. Ltd. | 01.06.2018 | 200 | Tuticorin, Tamil Nadu | 30.08.2018 | 09.09.2020 (46 MW); 24.10.2020 (30 MW); 16.11.2020 (18 MW); 04.03.2021 (12 MW); 16.04.2021 (18 MW); 10.06.2021 (12 MW); 13.08.2021 (10 MW); 18.09.2021 (12 MW); 21.10.2021 (10 MW) | 168
5 | WPD-ISTS-T4-IWISL-P1-50GJ | Suswind Power Private Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 | - | 0
6 | WPD-ISTS-T4-IWISL-P2-50GJ | Flutter Wind Energy Private Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 | - | 0
7 | WPD-ISTS-T4-ARETNL-P1-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 | Project stands terminated. | 0
8 | WPD-ISTS-T4-ARETNL-P2-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 |  | 0
9 | WPD-ISTS-T4-ARETNL-P3-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 |  | 0
10 | WPD-ISTS-T4-ARETNL-P4-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 |  | 0
11 | WPD-ISTS-T4-ARETNL-P5-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 |  | 0
12 | WPD-ISTS-T4-ARETNL-P6-50GJ | Adani Wind Energy Kutchh Two Limited | 01.06.2018 | 50 | Kutch, Gujarat | 30.08.2018 |  | 0
13 | WPD-ISTS-T4-MEPL-P1-300TN | Mytrah Vayu (Brahmaputra) Pvt Ltd | 01.06.2018 | 300 | Coimbatore, Tamil Nadu | 30.08.2018 | WPD unilaterally terminated the PPA and filed the case in CERC. Hearing in the matter is ongoing. | 0
14 | WPD-ISTS-T4-RWETNPL-P1-265GJ | ReNew Wind Energy (TN) Private Limited | 01.06.2018 | 265 | Kutch, Gujarat | 30.08.2018 | Project stands terminated. | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-V)
1 | WPD-ISTS-T5-TPL-P1-115GJ | Torrent Solargen Limited | 24.10.2018 | 115 | Devbhoomi Dwarka, Gujarat | 22.01.2019 | 26.05.2023 (27 MW) | 27
2 | WPD-ISTS-T5-AGEL-P1-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 | Project stands terminated. | 0
3 | WPD-ISTS-T5-AGEL-P2-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 |  | 0
4 | WPD-ISTS-T5-AGEL-P3-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 |  | 0
5 | WPD-ISTS-T5-AGEL-P4-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 |  | 0
6 | WPD-ISTS-T5-AGEL-P5-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 |  | 0
7 | WPD-ISTS-T5-AGEL-P6-50GJ | Adani Wind Energy Kutchh Four Ltd | 24.10.2018 | 50 | Kutch, Gujarat | 22.01.2019 |  | 0
8 | WPD-ISTS-T5-AC-P1-300GJ | Netra Wind Private Limited | 24.10.2018 | 300 | Kutch, Gujarat | 22.01.2019 | 10.04.2023 (55 MW) | 55
9 | WPD-ISTS-T5-SKRPL-P1-300GJ | Sitac Kabini Renewables Private Limited | 24.10.2018 | 300 | Kutch, Gujarat | 22.01.2019 | 10.08.2022 (94.5 MW); 18.08.2022 (21.6 MW); 23.08.2022 (18.9 MW); 24.08.2022 (13.5 MW); 01.09.2022 (10.8 MW); 05.09.2022 (13.5 MW); 20.09.2022 (35.1 MW); 23.09.2022 (10.8 MW); 10.10.2022 (10.8 MW); 21.11.2022 (13.5 MW); 05.12.2022 (13.5 MW); 29.05.2023 (29.7 MW); 30.05.2023 (13.8 MW) | 300
10 | WPD-ISTS-T5-EEIPL-P1-175KA | Boreas Renewable Energy Private Limited | 24.10.2018 | 175 | Bellary, Karnataka | 22.01.2019 | - | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-VI)
1 | WPD-ISTS-T6-AREPGL-P1-150GJ | Adani Wind Energy Kutchh Three Limited | 17.06.2019 | 150 | Kutch, Gujarat | 15.09.2019 | 10.03.2021 (14.7 MW); 17.03.2021 (30.5 MW); 09.04.2021 (43.8 MW); 04.05.2021 (28.6 MW); 01.06.2021 (32.4 MW) | 150
2 | WPD-ISTS-T6-AREPGL-P2-100GJ | Adani Wind Energy Kutchh Three Limited | 17.06.2019 | 100 | Kutch, Gujarat | 15.09.2019 | 2021-03-06 | 100
3 | WPD-ISTS-T6-OEPL-P1-300TN | Ostro Kannada Power Pvt Ltd | 17.06.2019 | 300 | Bellary and Davanagere, Karnataka | 15.09.2019 | 24.09.2021 (63 MW); 11.10.2021 (10.50 MW); 19.10.2021 (10.50 MW); 26.10.2021 (16.8 MW); 12.11.2021 (14.7 MW); 30.11.2021 (10.5 MW); 17.12.2021 (10.5 MW); 26.07.2022 (37.8 MW); 02.08.2022 (14.7 MW); 09.09.2022 (10.5 MW) | 199.5
4 | WPD-ISTS-T6-PL-P1-50.6GJ | Powerica Limited | 17.06.2019 | 50.6 | Devbhoomi Dwarka, Gujarat | 15.09.2019 | 02.06.2022 (24.3 MW); 18.08.2022 (26.3 MW) | 50.6
5 | WPD-ISTS-T6-SSPTPL-P1-274.4MH | Adani Wind Energy MP One Private Limited | 17.06.2019 | 274.4 | Dhar, Ratlam and Ujjain in Madhya Pradesh | 15.09.2019 | 10.09.2022 (205.2 MW); 17.09.2022 (69.2 MW) | 274.4
6 | WPD-ISTS-T6-SSPTPL-P2-50MH | Adani Wind Energy MP One Private Limited | 17.06.2019 | 50 | Dhar, Ratlam and Ujjain in Madhya Pradesh | 15.09.2019 | 10.09.2022 (45.9 MW); 17.09.2022 (4.1 MW) | 50
7 | WPD-ISTS-T6-SESPL-P1-150GJ | Morjar Windfarm Development Pvt. Ltd. | 17.06.2019 | 150 | Kutch, Gujarat | 15.09.2019 | 10.08.2022 (67.5 MW); 08.09.2022 (13.5 MW); 09.12.2022 (10.8 MW); 01.06.2023 (24.3 MW); 02.06.2023 (16.2 MW) | 132.3
8 | WPD-ISTS-T6-ZREPL-P1-125KA | Zenataris Renewable Energy Private Limited | 17.06.2019 | 125 | Bellary, Karnataka | 15.09.2019 | Project cancelled. | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-VII)
1 | WPD-ISTS-T7-BWEPL-P1-200GJ | Betam Wind Energy Private Limited | 19.06.2019 | 200 | Devbhumi Dwarka, Gujarat | 18.10.2019 | Project cancelled. | 0
2 | WPD-ISTS-T7-OEPL-P1-50GJ | Ostro Energy Private Limited | 19.06.2019 | 50 | Kutch, Gujarat | 18.10.2019 | 12.11.2021 (11 MW); 03.12.2021 (11 MW) 29.03.2022 (13.2 MW); 09.05.2022 (11 MW); 05.12.2022 (3.8 MW) | 50
3 | WPD-ISTS-T7-SPUPL-P1-100MP | Sprng Wind Energy Private Limited | 19.06.2019 | 100 | Dhar, Madhya Pradesh | 18.10.2019 | Project stands terminated. | 0
4 | WPD-ISTS-T7-AREPGL-P1-130GJ | Adani Wind Energy Kutchh Five Limited | 19.06.2019 | 130 | Kutch, Gujarat | 18.10.2019 | 15.08.2021 (53.6 MW); 12.10.2021 (14.70 MW); 04.01.2023 (50.2 MW); 25.05.2023 (11.5 MW) | 130
1800 MW ISTS-connected Wind Power Projects (Tranche-VIII)
1 | WPD-ISTS-T8-CLPIPL-P1-250GJ | Apraava Energy Pvt Ltd | 28.09.2019 | 250.8 | Devbhumi Dwarka, Gujarat | 21.05.2020 | 06.04.2023 (52.5 MW); 05.05.2023 (29.4 MW); 26.05.2023 (25.2 MW) | 107.1
2 | WPD-ISTS-T8-AEIPL-P1-190GJ | Tunga Renewable Energy Pvt Ltd | 28.09.2019 | 190 | Koppal, Karnataka | 21.05.2020 | - | 0
2500 MW ISTS-connected Wind Power Projects (Tranche-IX)
1 | WPD-ISTS-T9-VEVPL-P1-160MW | Vena Energy Vidyuth Pvt Ltd | 25.09.2020 | 160 | Tiruppur, Tamil Nadu | 31.03.2021 | - | 0
2 | WPD-ISTS-T9-JSWSL-P1-540MW | JSW Renew Energy Ltd | 25.09.2020 | 540 | Koppal, Karnataka | 31.03.2021 | - | 0
3 | WPD-ISTS-T9-JSWSL-P2-270MW | JSW Renew Energy Ltd | 25.09.2020 | 270 | Tuticorin, Tenkasi, Tirunelveli, Tamil Nadu | 15.07.2021 | - | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-X)
1 | WPD-ISTS-T10-AREHFL-P1-300MW | Adani Renewable Energy Seven Ltd | 19.03.2021 | 300 | Koppal, Karnataka | 10.09.2021 | - | 0
2 | WPD-ISTS-T10-ARPSPL-P1-300MW | Ayana Renewable Power Six Pvt Ltd | 19.03.2021 | 300 | Gadag, Karnataka | 10.09.2021 | - | 0
3 | WPD-ISTS-T10-EPMPL-P1-150MW | Viento Renewables Pvt Ltd | 19.03.2021 | 150 | Osmanabad, Maharashtra | 10.09.2021 | - | 0
4 | WPD-ISTS-T10-JSWFEL-P1-150MW | JSW Renew Energy Two Ltd | 19.03.2021 | 150 | Tiruppur, Tamil Nadu | 10.09.2021 | 04.12.2022 (27 MW); 21.04.2023 (51.3 MW); 09.05.2023 (13.5 MW); 26.05.2023 (24.3 MW); 05.06.2023 (13.5 MW) | 129.6
5 | WPD-ISTS-T10-JSWFEL-P2-300MW | JSW Renew Energy Two Ltd | 19.03.2021 | 300 | Thoothukudi, Tamil Nadu | 10.09.2021 | - | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-XI)
1 | WPD-ISTS-T11-RNUPL-P1-300MW | ReNew Naveen Urja Private Limited | 20.10.2021 | 300 | Gadag, Karnataka | 30.06.2022 | - | 0
2 | WPD-ISTS-T11-GIWEL-P1-180MW | Green lnfra Wind Energy Limited | 20.10.2021 | 180 | Koppal, Karnataka | 30.06.2022 | - | 0
3 | WPD-ISTS-T11-ARPL-P1-150MW | Anupavan Renewables pvt Ltd | 20.10.2021 | 150 | Osmanabad, Maharashtra | 30.06.2022 | - | 0
4 | WPD-ISTS-T11-AREHFL-P1-450MW | Adani Renewable Energy Four Ltd | 20.10.2021 | 450 | Gadag, Karnataka | 30.06.2022 | - | 0
5 | WPD-ISTS-T11-APIPL-P1-120MW | Two Wind Energy Pvt Ltd | 20.10.2021 | 120 | Koppal, Karnataka | 30.06.2022 | - | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-XII)
1 | WPD-ISTS-T12-HRPL-P1-300MW | Halvad Renewables Pvt Ltd | 12.07.2022 | 300 | Koppal & Gadag, Karnataka | 2023-03-29 | - | 0
2 | WPD-ISTS-T12-JSWNEL-P1-300MW | JSW Renew Energy Three Ltd | 12.07.2022 | 300 | Osmanabad, Maharashtra | 2023-03-29 | - | 0
3 | WPD-ISTS-T12-NTPCREL-P1-200MW | NTPC Renewable Energy Ltd | 12.07.2022 | 200 | Kutch, Gujarat | 2023-03-29 | - | 0
4 | WPD-ISTS-T12-TPL-P1-300MW | Torrent Saurya Urja 2 Pvt Ltd | 12.07.2022 | 300 | Bagalkot, Karnataka | 2023-03-29 | - | 0
1200 MW ISTS-connected Wind Power Projects (Tranche-XIII)
1 | WPD-ISTS-T13-SJVNL-P1-100MW | SJVN Ltd | 19.01.2023 | 100 | Gujarat | - | - | 0
2 | WPD-ISTS-T13-SIIIBV-P1-300MW | Scatec India II B.V. | 19.01.2023 | 300 | Kushtagi, Karnataka | - | - | 0
3 | WPD-ISTS-T13-TGPXIPL-P1-200MW | Teq Green Power XI Pvt Ltd | 19.01.2023 | 200 | Maharashtra | - | - | 0
5187.6