## Amendment - 2
SECI/C&P/TD/2020/LEH/20S/20B
Design, Engineering, Supply, Construction, Erection, Testing, Commissioning and O&M of 20 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Phyang, Leh, UT of Ladakh, India
Sl. No. | Section | Page No. | Clause | Original Version | Amendment
1 | Section III Bid Data Sheet | 2 of 4 | Clause No 3 : NUMBER OF BIDS PER BIDDER (ITB 4.0) | Replace the existing clause by the following: Bidder shall submit only 'one [01] Bid' per bidder in the Bidding Process. A Bidder who submits or participates in more than 'one [01] Bid' will cause all the proposals in which the Bidder has participated to be disqualified. | Replace the existing clause by the following: Bidder shall submit only 'one [01] Bid' per bidder in the Bidding Process. A Bidder who submits or participates in more than 'one [01] Bid' will cause all the proposals in which the Bidder has participated to be disqualified. A Bidder including its Parent, Affiliate or Ultimate Parent or any Group Company may submit a single bid. Note: In case a common Company/Companies directly or indirectly hold(s) more than 10% but less than 26% shareholding in more than one Bidder participating in the Tender, each of such Bidders will be required to submit the Disclosure as per the attached format. In all other cases, this disclosure is not required & standard forms & formats will be applicable.
2 | Section VI Sample Forms & Formats | 5 of 57 | clause No 2 : Form 0, Covering Letter | We, the undersigned…. [insert name of the ‘Bidder’] having read, examined and understood in detail the tender Document for “Tender for Design, Engineering, Supply, Construction, Erection, Testing, Commissioning and O&M of 20 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Phyang, Leh, UT of Ladakh, India” hereby submit our Bid comprising of Techno Commercial Bid and Price Bid. We confirm that neither we nor any of our Parent Company/ Affiliate / Ultimate Parent Company has submitted Bid other than this Bid directly or indirectly in response to the aforesaid tender | Replace the existing clause by the following: We, the undersigned…. [insert name of the ‘Bidder’] having read, examined and understood in detail the tender Document for “Tender for Design, Engineering, Supply, Construction, Erection, Testing, Commissioning and O&M of 20 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Phyang, Leh, UT of Ladakh, India” hereby submit our Bid comprising of Techno Commercial Bid and Price Bid. "We confirm that neither we nor any of our Parent Company/ Affiliate / Ultimate Parent Company has submitted Bid other than this Bid directly or indirectly in response to the aforesaid tender." Note: In case a common Company/Companies directly or indirectly hold(s) more than 10% but less than 26% shareholding in more than one Bidder participating in the Tender, each of such Bidders will be required to submit the Disclosure as per the attached format. In such a case, the above mentioned highlighted declaration/statement will be modified suitably by the bidder.In all other cases, this disclosure is not required & standard covering letter & other forms & formats will be applicable.
3 | Section VI sample Forms & Formats | 33 of 57 | Form 12, DECLARATION REGARDING THE MANDATORY PROCUREMENT OF SOLAR INVERTERS FROM CLASS I LOCAL SUPPLIERS | DECLARATION REGARDING THE MANDATORY PROCUREMENT OF SOLAR INVERTERS FROM CLASS I LOCAL SUPPLIERS | Forms stands Null & Void and is hereby withdrawn
4 | Section V Special Conditions of Contract | 6 of 10 | Clause No 11 :Schedule of Rates & Payments (GCC clause 80.1) | Add following to the existing clause: All payment shall be made against invoices raised in line with the approved billing break up under individual heads of Supply, Services and Civil works. Following general payment terms will be followed A. The payment for the Supply Portion of the First Contract (Supply & Services Contract) shall be made as per the following terms and conditions: i) Interest bearing adjustable initial advance (OPTIONAL) of 10% of the Contract Value (i.e., total sum of all the Supply Contract) shall be released to successful bidder upon receipt of unconditional acceptance of NOA, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final commissioning total amounting to 110% of total advance amount. The ABG needs to be submitted in addition to the Contract Performance Security. The annual interest rate shall be calculated based on SBI one-year MCLR + 3.5% as applicable. Successful bidder will be required to submit the individual ABGs on individual site basis for claiming the advance amount. ii) Seventy percent (70%) payments shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause i) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality, submission of the certificate by the Executing Agency’s authorized representative that the item(s) have been received and MDCC (Material Dispatch Clearance Certificate) issued by Employer’s authorized representative in original. (a) If Successful Bidder has opted for advance then, Ten percent (10%) (Full amount of advance) shall be adjusted while making payments of this installment. Also, up-to-date accrued interest shall also be recovered. (iii) Twenty percent (20%) payments shall be paid against successful erection, testing and commissioning of materials at site and Operational Acceptance of the Facility (Part/Complete facility). pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and documents. (iv) Final Ten percent (10%) payment of Supplies shall be paid after CUF demonstration on completion of first year of O&M of the complete Facility pursuant to submission of all requisite documentation. However, this Payment may also be released after demonstration of PR and submission of all requisite documentation on the submission of additional Bank Guarantee of equivalent amount. This BG shall be valid up to demonstration of CUF for the successful first year of Operation. However, in case of delay, the BG shall be extended suitably. B. The payment for the Service Portion of the First Contract (Supply & Services Contract) shall be made as per the following terms and conditions. No Initial Advance Payment shall be made against the Service Portion Part. i) For Freight and Insurance Portion, the payment shall be made in line with Supply Portion of the First Contract, as described in point A (ii) of this clause, without releasing any initial advance. The complete payment of the freight will be done along with the respective deliveries of the supply portion at site. ii) For Erection, Testing and Commissioning Portion, the payment shall be made as detailed below: - (a) Eighty Percent (80%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid on pro-rata basis on completion of installation of equipment on certification by the Engineer-In-Charge/ Project Manager for the quantum of work completed after successful clearance of quality check points involved in the quantum of work billed. (b) Ten Percent (10%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid on Operational Acceptance of the Facility (Part/Complete facility). pursuant to successful integration with existing internal grid system, Guarantee Tests and demonstration of PR. (c) Final Ten percent (10%) payments shall be paid after CUF demonstration after first year of O&M of the complete Facility pursuant to submission of all requisite documentation. However, this Payment may also be released after successful Guarantee Tests and demonstration of PR and submission of all requisite documentation on the submission of additional Bank Guarantee of equivalent amount. The BG shall be valid up to demonstration of CUF for the successful first year of Operation. However, in case of delay, the BG shall be extended suitably. iii) For Civil & Allied works portion, of the 1st contract, the payment shall be made as detailed below: (a) Eighty Percent (80%) of the total price of Civil Works shall be paid progressively on certification by the Project Manager/ Engineer In - Charge for the quantum of work completed/ Milestones achieved after successful clearance of quality check points involved in the quantum of work. (b) Ten Percent (10%) of the total price of Civil Works shall be paid on completion of all the civil works. (c) Final Ten (10%) of the total price of Civil Works shall be paid after CUF demonstration after first year of O&M of the complete Facility pursuant to completion of all the civil works including finishing and debris removal. However, this Payment may also be released after completion of all the civil works including finishing and debris removal on submission of Bank Guarantee of equivalent amount. The BG shall be valid up to demonstration of CUF for the successful first year of Operation. However, in case of delay, the BG shall be extended suitably. C. For the Second Contract (related to Operation & Maintenance Part), the payment shall be made as detailed below: - (a) Operation and Maintenance of the entire Project payment will be released on quarterly basis at the end of every quarter for each year till 10 (Ten) years. (i) Year 1 : OM -1 (ii) Year 2 : OM -2 (iii) Year 3 : OM -3 (iv) Year 4 : OM -4 (v) Year 5 : OM -5 (vi) Year 6 : OM -6 (vii) Year 7 : OM -7 (viii) Year 8 : OM -8 (ix) Year 9 : OM -9 (x) Year 10 : OM -10 In case of any default, Non-Performance or breach of contractual conditions of the O&M contract during the O&M period, the penalties/deductions, if applicable will be liable to be deducted from the Quarterly O&M payments first & then from the Contract Performance Security. | Add following to the existing clause: All payment shall be made against invoices raised in line with the approved billing break up under individual heads of Supply, Services and Civil works. Following general payment terms will be followed A. The payment for the Supply Portion of the First Contract (Supply & Services Contract) shall be made as per the following terms and conditions: i) Interest bearing initial advance (OPTIONAL) of 10% of the Contract Value (i.e., total sum of all the Supply Contract) shall be released to the contractor upon receipt of unconditional acceptance of NOA, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final commissioning total amounting to 110% of total advance amount. The ABG needs to be submitted in addition to the Contract Performance Security. The annual interest rate shall be calculated based SBI one-year MCLR as applicable. ii) Seventy percent (70%) payments shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause i) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality, submission of the certificate by the Executing Agency’s authorized representative that the item(s) have been received and MDCC (Material Dispatch Clearance Certificate) issued by Employer’s authorized representative in original. * In case the Interest-bearing initial advance (OPTIONAL) of 10% of the Contract Value is not availed by the contractor, then this 10% payment amount will be payable along with the point No A ii) along with the 70% payment milestone. (iii) Ten percent (10%) payments shall be paid against successful erection, testing and commissioning of materials on pro rata basis at site. (iv) Final Ten percent (10%) payment of Supplies shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. B. The payment for the Service Portion of the First Contract (Supply & Services Contract) shall be made as per the following terms and conditions. No Initial Advance Payment shall be made against the Service Portion Part. i) For Freight and Insurance Portion, the payment shall be made in line with Supply Portion of the First Contract, as described in point A (ii) of this clause, without releasing any initial advance. The complete payment of the freight will be done along with the respective deliveries of the supply portion at site. ii) For Erection, Testing and Commissioning Portion, the payment shall be made as detailed below: - (a) Eighty Percent (80%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid on pro-rata basis on completion of installation of equipment on certification by the Engineer-In-Charge/ Project Manager for the quantum of work completed after successful clearance of quality check points involved in the quantum of work billed. (b) Ten Percent (10%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned. (c) Final Ten percent (10%) payment of Supplies shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. iii) For Civil & Allied works portion, of the 1st contract, the payment shall be made as detailed below: (a) Eighty Percent (80%) of the total price of Civil Works shall be paid progressively on certification by the Project Manager/ Engineer In - Charge for the quantum of work completed/ Milestones achieved after successful clearance of quality check points involved in the quantum of work. (b) Ten Percent (10%) of the total price of Civil Works shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned.. (c) Final Ten percent (10%) payment of Supplies shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. C. For the Second Contract (related to Operation & Maintenance Part), the payment shall be made as detailed below: - (a) Operation and Maintenance of the entire Project payment will be released on quarterly basis at the end of every quarter for each year till 10 (Ten) years. (i) Year 1 : OM -1 (ii) Year 2 : OM -2 (iii) Year 3 : OM -3 (iv) Year 4 : OM -4 (v) Year 5 : OM -5 (vi) Year 6 : OM -6 (vii) Year 7 : OM -7 (viii) Year 8 : OM -8 (ix) Year 9 : OM -9 (x) Year 10 : OM -10 In case of any default, Non-Performance or breach of contractual conditions of the O&M contract during the O&M period, the penalties/deductions, if applicable will be liable to be deducted from the Quarterly O&M payments first & then from the Contract Performance Security. D. All the payment shall be released from Owner’s Head Office, New Delhi upon submission of Original Documents like MDCC, delivery challan, warranty certificate, LR, WCC, MRN, commissioning certificate, handing over certificate, Insurance, PF, ESI, etc as required and mentioned against each Milestone payment, duly certified by the authorized representative of the Employer/Owner.
5 | VII-B Technical Specifications | 17 of 182 | 4.4.5 | Circuit Breaker of appropriate voltage and current rating shall be provided at the output to isolate the PCU from grid in case of faults. | Circuit Breaker or Relays of appropriate voltage and current rating shall be provided at the output to isolate the PCU from grid in case of faults.
6 | VII-B Technical Specifications | 16 of 182 | 4.2.1 | The Inverter Supplier should have supplied minimum 5 GW capacity globally or 1 GW in India in the past 5 years (as on last date of the bid submission). The solar inverter supplier shall be Class-I local supplier as per MNRE Order dated 23rd Sep, 2020 on Public Procurement (Preference to Make in India) to provide for Purchase Preference (linked with local content) in respect of Renewable Energy (RE) Sector. | The Inverter Supplier should have supplied minimum 5 GW capacity globally or 1 GW in India in the past 5 years (as on last date of the bid submission).
7 | VII-C Special Technical Specifications | 8 of 8 | 6.1 | New Clause | The Main Approach Road to the Plant shall have a wearing course of 20 mm thick pre-mix carpet topping. All other specifications shall be as per Clause 6.3 of Section VII-B, Technical Specifications. Adequate slope protection measure shall be built , as required.
8 | VII-B Technical Specifications | 111 of 182 | 10.10.2 | For estimation of design wind loads on purlins (Table 8 of IS 875- Part 3), WL (downward) and WL (upward) on modules (laid in the profile of mono slope canopy) shall be applied such that the center of pressure should be at (0.3 × length of canopy) from windward end (for simplicity, the wind load distribution may be taken as triangular with max. value at windward end). Solidity ratio (∅) shall be taken as 0.5. | For estimation of design wind loads on purlins (Table 8 of IS 875- Part 3), WL (downward) and WL (upward) on modules (laid in the profile of mono slope canopy) shall be applied such that the center of pressure should be at (0.3 × length of canopy) from windward end (for simplicity, the wind load distribution may be taken as triangular with max. value at windward end). Solidity ratio (∅) shall be taken as 0. Apart from this distribution, any other distribution of wind load based on wind tunnel studies may be followed subject to the approval of the employer. In case the contractor proposes to use wind tunnel study for the purpose of evaluation of wind pressure distribution on MMS, the following have to be ensured: i. Independent site-specific study shall be done giving due consideration to topography, type of terrain, MMS orientation, and other relevant parameters. ii. It must be done from an institute of repute (IITs in India). If the study is done by any reputed international facility the study results must be vetted by any of the IITs in India.