## Amendment 3
SECI/C&P/TD/2021/CG/100
Tender for Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 100 MW (AC) Solar PV Project with Land having 10 years plant O&M at Chhattisgarh, India.
Sl. No. | Section | Page No. | Clause | Original Version | Amendment
1 | Invitation for Bids | 6 of 10 | Bid Information Sheet, Point (A) | Complete transfer of ownership of encumbrance free land in favor of SECI Ltd, Design, engineering, procurement & supply of equipment and materials, testing at manufacturers’ works, multi ………………………... | Complete transfer of ownership of encumbrance free land/lease of encumbrance free Govt/PSU/Private Land in favor of SECI Ltd, Design, engineering, procurement & supply of equipment and materials, testing at manufacturers’ works, multi ………………………...
2 | Invitation for Bids | 10 of 10 | 6 (iv) | (iv) Fourth Contract (Acquisition & Transfer of Land): For the acquisition & Transfer of Land including developed infrastructure (if any) | Fourth Contract (Acquisition & Transfer of Land): For the acquisition/lease transfer of Land including developed infrastructure (if any)/ Lease Agreement of encumbrance free GovtPSU/Private land. In both the cases of lease/sub lease Deed the lease agreement to be executed by SECI with the GovtPSU/Private land owners will be executed for min period of 27 years from date of signing of lease agreement..
3 | Instruction to Bidders | 23 of 48 | 32.3.6 | 32.3.6 The Employer's comparison will include the costs resulting from application of the evaluation procedures described below: The Evaluated Bid Value (EBV) shall be calculated using the following method: i. Design, Supply and Installation (DSI) or EPC Price i.e., Total sum of Schedule Nos 1,2 & 3 including: • The price comprising of Plant and Mandatory Spare Parts Supplied from Abroad on CIP basis (i.e. including BCD+SWS, SGD/ADD or any other duty or taxes) as per Schedule No 1/SOR 1, Plus • Ex Works basis Supply of Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country on EXW basis (i.e. including GST) as per Schedule No 2/SOR 2, Plus • Freight, Design, Civil & Installation and Other Services including GST/Taxation as per Schedule No 3/SOR 3, Plus ii. NPV of O&M for the total O&M period in years, as mentioned in the tender document i.e., Schedule No 4/SOR 4 including • Net Present Value (NPV) of O&M Price including GST/Taxation for the total O&M period for the plant facilities to be calculated at a discounting rate as per Price Schedule No 4/SOR 4. Discounting Rate for NPV calculation considered is 8.61% Evaluated Bid Value (EBV), as given under Schedule No 5/SOR 5 = sum of (i) and (ii) Schedule No. 1: The price comprising of Plant and Mandatory Spare Parts Supplied from Abroad on CIP basis (i.e. including BCD+SWS, SGD/ADD or any other duty or taxes) Schedule No. 2: Ex Works basis Supply of Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country on EXW basis (i.e. including GST) Schedule No. 3: Freight, Design, Civil & Installation and Other Services including GST/Taxation Schedule No. 4: Net Present Value (NPV) of O&M Price including GST/Taxation for the total O&M period for the plant facilities to be calculated at a given discounting rate Schedule No. 5: Grand Summary (Schedule Nos.1 to 4) The terms EXW etc., shall be governed by the rules prescribed in the current edition of Incoterms, published by the International Chamber of Commerce, 38, Course Albert 1er, 75008, Paris, France | 32.3.6 The Employer's comparison will include the costs resulting from application of the evaluation procedures described below: The Evaluated Bid Value (EBV) shall be calculated using the following method: i. Design, Supply and Installation (DSI) or EPC Price i.e., Total sum of Schedule Nos 1,2 & 3 (Considering Land Schedule)** including: • The price comprising of Plant and Mandatory Spare Parts Supplied from Abroad on CIP basis (i.e. including BCD+SWS, SGD/ADD or any other duty or taxes) as per Schedule No 1/SOR 1, Plus • Ex Works basis Supply of Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country on EXW basis (i.e. including GST) as per Schedule No 2/SOR 2, Plus • Freight, Design, Civil & Installation and Other Services including GST/Taxation as per Schedule No 3/SOR 3, Plus ** The cost of Land to be filled under SOR 2 is to be taken from the "Land Schedule" as provided under the revised Schedule of Rates (SOR) attached. Bidder should fill the Land cost from Cell No G 39 of the "Land Schedule" in case of Lease of the Govt/PSU/Private Land & Cell No K 39 of the "Land Schedule" in case of sale Deed/Title Transfer to SECI. In case of any deviations, the land cost as mentioned under "Land Schedule" under the Schedule of Rates (SOR) will prevail. ii. NPV of O&M for the total O&M period in years, as mentioned in the tender document i.e., Schedule No 4/SOR 4 including • Net Present Value (NPV) of O&M Price including GST/Taxation for the total O&M period for the plant facilities to be calculated at a discounting rate as per Price Schedule No 4/SOR 4. Discounting Rate for NPV calculation considered is 8.61% Evaluated Bid Value (EBV), as given under Schedule No 5/SOR 5 = sum of (i) and (ii) Schedule No. 1: The price comprising of Plant and Mandatory Spare Parts Supplied from Abroad on CIP basis (i.e. including BCD+SWS, SGD/ADD or any other duty or taxes) Schedule No. 2: Ex Works basis Supply of Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country on EXW basis (i.e. including GST) Schedule No. 3: Freight, Design, Civil & Installation and Other Services including GST/Taxation Schedule No. 4: Net Present Value (NPV) of O&M Price including GST/Taxation for the total O&M period for the plant facilities to be calculated at a given discounting rate Schedule No. 5: Grand Summary (Schedule Nos.1 to 4) Land Schedule : The cost of Land to be filled under SOR 2 is to be taken from the "Land Schedule" as provided under the revised Schedule of Rates (SOR) attached. The terms EXW etc., shall be governed by the rules prescribed in the current edition of Incoterms, published by the International Chamber of Commerce, 38, Course Albert 1er, 75008, Paris, France
4 | Annexure to BDS | 3 of 7 | 1.2 | TECHNICAL ELIGIBILITY CONDITIONS Bidders can participate through any one of the below mentioned qualifying routes. The Bidder shall be considered meeting Technical Eligibility criteria either from Route I or Route II. Route I IA. The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, Supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), Installation and Commissioning of Grid connected Solar PV Power Plant of cumulative Capacity not less than 50 (Fifty) MW (AC) in last seven Financial years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND IB. The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), installation & commissioning of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW (AC) or above in last seven Financial years last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. OR Route II IIA. The bidder must have experience in execution of Ground mounted Solar Projects as a Developer of Grid-connected Solar PV Power Plant(s) of cumulative Capacity not less than 50 (Fifty) MW (AC) in last seven Financial years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND IIB. The bidder must have experience in execution of Ground mounted Solar Projects as a Developer of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW (AC) or above in last seven Financial years and till last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. | TECHNICAL ELIGIBILITY CONDITIONS Bidders can participate through any one of the below mentioned qualifying routes. The Bidder shall be considered meeting Technical Eligibility criteria either from Route I or Route II. Route I IA. The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, Supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), Installation and Commissioning of Grid connected Solar PV Power Plant of cumulative Capacity not less than 50 (Fifty) MW (AC) in last Ten Financial years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND IB. The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), installation & commissioning of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW (AC) or above in last Ten Financial years last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. OR Route II IIA. The bidder must have experience in execution of Ground mounted Solar Projects as a Developer of Grid-connected Solar PV Power Plant(s) of cumulative Capacity not less than 50 (Fifty) MW (AC) in last Ten Financial years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND IIB. The bidder must have experience in execution of Ground mounted Solar Projects as a Developer of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW (AC) or above in last Ten Financial years and till last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission.
5 | Annexure to BDS | 3 of 7 | 1.2 | FINANCIAL ELIGIBILITY CONDITIONS The Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2017-18, 2018-19 & 2019-20) should be INR 208 Crores/- (Indian Rupees Two hundred & eight Crores only). MAAT shall mean Revenue from Operations as incorporated in the profit & loss account excluding other income, e.g. sale of fixed assets. This must be the individual Company’s turnover and not that of any group of Companies. A summarized sheet of average turnover, certified by a practicing Chartered Accountant/Statutory Auditor should be compulsorily enclosed along with corresponding annual accounts. And.............................................................................. | FINANCIAL ELIGIBILITY CONDITIONS The Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2018-19, 2019-20 & 2020-21) should be INR 208 Crores/- (Indian Rupees Two hundred & eight Crores only). MAAT shall mean Revenue from Operations as incorporated in the profit & loss account excluding other income, e.g. sale of fixed assets. This must be the individual Company’s turnover and not that of any group of Companies. A summarized sheet of average turnover, certified by a practicing Chartered Accountant/Statutory Auditor should be compulsorily enclosed along with corresponding annual accounts. And..............................................................................
6 | Section V Special Conditions of Contract | 2 of 12 | 3.2 & 3.3 | Complete transfer of ownership of minimum 50% land in favor of the employer : D+06 Months Complete transfer of ownership of remaining of total land in favor of the employer : D+10 Months However, The Time for Commissioning for the 100 MW (AC) Solar PV Project with Land handover & with all other associated equipment as per this tender document in total shall be 18 (Eighteen) Months from the Date of the Notification of Award NOA/LOA/LOI. | Complete transfer of ownership of minimum 50% land/ lease of 50% Govt/PSU/Private land in favor of the employer : D+06 Months Complete transfer of ownership of remaining of total land/lease of remaining Govt/PSU/Private land in favor of the employer : D+10 Months However, The Time for Commissioning for the 100 MW (AC) Solar PV Project with Land handover & with all other associated equipment as per this tender document in total shall be 18 (Eighteen) Months from the Date of the Notification of Award NOA/LOA/LOI.
7 | Section V Special Conditions of Contract | 4 of 12 | Location of Site (GCC clause 2.1.a) | Replace existing clause regarding location of the site with following: Land: a. The minimum quantum of Land required for the project is 400 Acres & bidders are required to consider this minimum Land requirement while bidding. However, bidders are required to assess judicially the total Land requirement for the project depending upon shape, Module efficiency design etc. and should bid accordingly The proposed Solar PV Project is to set up at the identified land location by the contractor in the state of Chhattisgarh, which will be identified, acquired & purchased by the contractor on employer’s behalf & same shall be transferred in the name of employer, in line with the timelines & provisions of the land transfer details as stipulated in the tender documents. b. The total Land offered by the Bidder will be transferred in favour of the Employer, covering relevant charges including all charges, Charges related to Developed Infrastructure (if any), all fees / charges towards infrastructure development, application, approvals, clearances, registration fees, documentation fee, Stamp Duty and / or other expenditure incurred upto the execution of Sale Deed in favour of the Employer. The Land charges shall also be inclusive of all applicable Taxes, Duties and Levies payable, as of Seven (7) days prior to the date of submission of Price Bid and Employer shall not bear responsibility of the same. c. The following documents are required to be submitted as per the Land delivery milestones mentioned under clause 3.2 & 3.3 of the SCC above, to establish clear title of the land has been transferred to the employer: i. Transfer Permission by the Authority ii. Title documents along with the chain documents with the land upto 25 years iii. Ten (10) years latest Non-encumbrance certificate by Sub-registrar iv. Mutation Certificate / Entry in Land Records according to local laws v. No Dues Certificate vi. Indemnity Bond/ Undertaking as per the Employer’s format in line with requirement of GCC vii. Payment receipt of Property Tax/Diversion Fee or Tax/other municipal & Development Tax as the case may be viii. Affidavit of the contractor to the effect that proper Due Diligence has been conducted with respect to the land and it is transferred to the employer in good faith & due consideration has been received by bonafide land owner. d. The Contractor shall indemnify and hold harmless the Employer and its employees and officers for a period up to 25 years in case of private land from the date of the transfer of the land from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any encumbrance on the project land arising out in relation to the transfer of title of the land in favor of the Employer. e. If any proceedings are brought or any claim is made against the Employer arising out of the, the Employer shall promptly give the Contractor a notice thereof, and the Contractor may at its own expense and in the Employer’s, name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf at the risk and cost of Contractor. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. f. The Bidder at the Bidder’s own responsibility, cost and risk shall inspect, examine & purchase the land and its surrounding, and shall satisfy themselves fully before submitting bids as to the form and nature of the site, the geological conditions decisive for the success of the project, the means of access to the site, the loading and unloading facilities etc. In general, the Bidders shall themselves obtain all necessary information as to risks, contingencies and other circumstances susceptible to influence or affect their bids. g. Bidders shall acquaint themselves on their own responsibility with Land laws and regulations in India under which the work is to be performed including those which may influence, in general or in detail, design, supply, transportation, erection, operation of the equipment and requirement of manpower. Any failure or neglect to do so will not absolve the potential Contractor from his contractual obligation. h. Prospective Bidders are advised to carefully read the Tender documents along with Annexures, understand them in the proper perspective and then fill the Technical Bid Format, Commercial Bid Format and Price Bid Format (SOR). | Land: a. The minimum quantum of Land required for the project is 400 Acres & bidders are required to consider this minimum Land requirement while bidding. However, bidders are required to assess judicially the total Land requirement for the project depending upon shape, Module efficiency design etc. and should bid accordingly The proposed Solar PV Project is to set up at the identified land location by the contractor in the state of Chhattisgarh, which will be identified, acquired & purchased/leased by the contractor on employer’s behalf & same shall be transferred/leased in the name of employer, in line with the timelines & provisions of the land transfer/lease details as stipulated in the tender documents. b. Bidders have the option of either offering the land to SECI on Sale Deed/Title Transfer basis or on Lease basis of the Govt/PSU/Private Land. Bidders also have the option of executing the Sale Deed/Lease deed directly with SECI or getting executed Sale Deed/Lease deed with the respective Land owner (s) or Govt/PSU/Private, as the case may be, with the facilitation of the contractor. However, the overall responsibility of getting the Sale/Lease Deed execution in any of the scenarios, lies solely with the contractor only. The land offered in case of lease can be Govt/PSU/Private Land. Bidders are required to either provide the cost for Sale deed or lease basis at a time & both kind of arrangements can not be offered simultaneously in this bid. The total Land offered by the Bidder will be transferred/leased in favour of the Employer, covering relevant charges including all charges, Charges related to Developed Infrastructure (if any), all fees / charges towards infrastructure development, application, approvals, clearances, registration fees, documentation fee, Stamp Duty and / or other expenditure incurred upto the execution of Sale Deed/lease deed in favour of the Employer. The Land charges shall also be inclusive of all applicable Taxes, Duties and Levies payable, as of Seven (7) days prior to the date of submission of Price Bid and Employer shall not bear responsibility of the same. c. The following documents are required to be submitted as per the Land delivery milestones mentioned under clause 3.2 & 3.3 of the SCC above, to establish clear title of the land has been transferred/leased to the employer: i. Transfer/lease Permission by the Authority. ii. Title/lease documents along with the chain documents with the land upto 25 years. iii. Ten (10) years latest Non-encumbrance certificate by Sub-registrar. iv. Mutation Certificate / Entry in Land Records according to local laws. v. No Dues Certificate. vi. Indemnity Bond/ Undertaking as per the Employer’s format in line with requirement of GCC. vii. Payment receipt of Property Tax/Diversion Fee or Tax/other municipal & Development Tax as the case may be. viii. Affidavit of the contractor to the effect that proper Due Diligence has been conducted with respect to the land and it is transferred/leased to the employer in good faith & due consideration has been received by bonafide land owner/Govt/PSU. d. The Contractor shall indemnify and hold harmless the Employer and its employees and officers for a period up to 27 years in case of "Acquisition & Transfer of Land" for Sale deed purpose & in case of leasing of Govt/PSU/Private Land, from the date of the transfer of the land from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any encumbrance on the project land arising out in relation to the transfer of title of the land in favor of the Employer. e. If any proceedings are brought or any claim is made against the Employer arising out of the, the Employer shall promptly give the Contractor a notice thereof, and the Contractor may at its own expense and in the Employer’s, name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf at the risk and cost of Contractor. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. f. The Bidder at the Bidder’s own responsibility, cost and risk shall inspect & examine the land and its surrounding, and shall satisfy themselves fully before submitting bids as to the form and nature of the site, the geological conditions decisive for the success of the project, the means of access to the site, the loading and unloading facilities etc. In general, the Bidders shall themselves obtain all necessary information as to risks, contingencies and other circumstances susceptible to influence or affect their bids. g. Bidders shall acquaint themselves on their own responsibility with Land laws and regulations in India under which the work is to be performed including those which may influence, in general or in detail, design, supply, transportation, erection, operation of the equipment and requirement of manpower. Any failure or neglect to do so will not absolve the potential Contractor from his contractual obligation. h. Prospective Bidders are advised to carefully read the Tender documents along with Annexures, understand them in the proper perspective and then fill the Technical Bid Format, Commercial Bid Format and Price Bid Format (SOR).
8 | Section V Special Conditions of Contract | 7 of 12 | 11 | Add following to the existing clause: All payment shall be made against invoices raised in line with the approved billing break up under individual heads of Supply, Services and Civil works. Following general payment terms will be followed which will be payable after complying the provision of ALMM clause only A. The payment for the Supply Portion of the First Contract (Supply Contract) shall be made as per the following terms and conditions: i) Interest bearing initial advance (OPTIONAL) of 10% of the Supply Contract value shall be released to the contractor upon receipt of unconditional acceptance of NOA, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final commissioning total amounting to 110% of total advance amount. The ABG needs to be submitted in addition to the Contract Performance Security. The annual interest rate shall be calculated based SBI one-year MCLR as applicable. ii) Seventy percent (70%) payments shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause i) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality, submission of the certificate by the Executing Agency’s authorized representative that the item(s) have been received and MDCC (Material Dispatch Clearance Certificate) issued by Employer’s authorized representative in original. * In case the Interest-bearing initial advance (OPTIONAL) of 10% of the Supply Contract Value is not availed by the contractor, then this 10% payment amount will be payable along with the point No A ii) along with the 70% payment milestone. ** The supply of Solar Modules & Inverters shall be scheduled in line with timelines for construction of transmission line. Any payment related to supplies will not be done by the employer till first 10 months of the award. In case transmission line gets ready, the timeline for payment against supplies will be reduced to 6 months. (iii) Ten percent (10%) payments shall be paid against successful erection, testing and commissioning of materials on pro rata basis at site. (iv) Final Ten percent (10%) payment of Supplies shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. B. The payment for the Service Portion of the Second Contract (Services Contract) shall be made as per the following terms and conditions. No Initial Advance Payment shall be made against the Service Portion Part. i) For Freight and Insurance Portion, the payment shall be made in line with Supply Portion of the Second Contract, as described in point A (ii) of this clause, without releasing any initial advance. The complete payment of the freight will be done along with the respective deliveries of the supply portion at site. ii) For Erection, Testing and Commissioning Portion, the payment shall be made as detailed below: - (a) Eighty Percent (80%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid on pro-rata basis on completion of installation of equipment on certification by the Engineer-In-Charge/ Project Manager for the quantum of work completed after successful clearance of quality check points involved in the quantum of work billed. (b) Ten Percent (10%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned. (c) Final Ten percent (10%) payment of Design, Engineering, Erection, Testing and Commissioning shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. iii) For Civil & Allied works portion, of the 1st contract, the payment shall be made as detailed below: (a) Eighty Percent (80%) of the total price of Civil Works shall be paid progressively on certification by the Project Manager/ Engineer In - Charge for the quantum of work completed/ Milestones achieved after successful clearance of quality check points involved in the quantum of work. (b) Ten Percent (10%) of the total price of Civil Works shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned. (c) Final Ten percent (10%) payment of Civil Works shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. C. For the Third Contract (related to Operation & Maintenance Part), the payment shall be made as detailed below: - (a) Operation and Maintenance of the entire Project payment will be released on quarterly basis at the end of every quarter for each year till 10 (Ten) years. (i) Year 1: OM -1 (ii) Year 2: OM -2 (iii) Year 3: OM -3 (iv) Year 4: OM -4 (v) Year 5: OM -5 (vi) Year 6: OM -6 (vii) Year 7: OM -7 (viii) Year 8: OM -8 (ix) Year 9: OM -9 (x) Year 10: OM -10 In case of any default, Non-Performance or breach of contractual conditions of the O&M contract during the O&M period, the penalties/deductions, if applicable will be liable to be deducted from the Quarterly O&M payments first & then from the Contract Performance Security. D. For the Fourth Contract (related to Acquisition & Transfer of Land), the payment shall be made as detailed below: - For Private land 1. Fifty Percent (50%) of the Land Cost Component of the Contract Price will be paid as under: (i) Acceptance of Notification of Award and Signing of the Contract Agreement. (ii) Submission of unconditional Bank Guarantees towards Contract Performance Securities. (iii) Submission of documents related to Land. (iv) Submission of application to State Nodal Agency for in-principle approval of state agency for availability of land or Acceptance of proposal/ application to State Nodal by state agency. (v) Successful completion of transfer of 50% of the total quantum of offered land on Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd and as per law for the same. 2. Balance Fifty Percent (50%) of the Land Cost Component of the Contract Price will be paid as under: (i) Fulfillment of Conditions mentioned at Clause D 1. (i), (ii), (iii), (iv), (v) above. (ii) Submission of documents related to Land. (iii) Submission of application to State Nodal Agency for in-principle approval of state agency for availability of land or Acceptance of proposal/ application to State Nodal by state agency. (iv) Successful completion of transfer of remaining 50% of the total quantum of offered land on Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd and as per law for the same. Notes: In case the contractor is not able to Successfully Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd for the remaining quantum of offered land, even after the additional grace period of 03 months over & above the allocated time, then its Proportionate CPS will be encashed. E. All the payment shall be released from Owner’s Head Office, New Delhi upon submission of Original Documents like MDCC, delivery challan, warranty certificate, LR, WCC, MRN, commissioning certificate, handing over certificate, Insurance, PF, ESI, etc as required and mentioned against each Milestone payment, duly certified by the authorized representative of the Employer/Owner. | Add following to the existing clause: All payment shall be made against invoices raised in line with the approved billing break up under individual heads of Supply, Services and Civil works. Following general payment terms will be followed which will be payable after complying the provision of ALMM clause only A. The payment for the Supply Portion of the First Contract (Supply Contract) shall be made as per the following terms and conditions: i) Interest bearing initial advance (OPTIONAL) of 10% of the Supply Contract value shall be released to the contractor upon receipt of unconditional acceptance of NOA, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final commissioning total amounting to 110% of total advance amount. The ABG needs to be submitted in addition to the Contract Performance Security. The annual interest rate shall be calculated based SBI one-year MCLR as applicable. ii) Seventy percent (70%) payments shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause i) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality, submission of the certificate by the Executing Agency’s authorized representative that the item(s) have been received and MDCC (Material Dispatch Clearance Certificate) issued by Employer’s authorized representative in original. * In case the Interest-bearing initial advance (OPTIONAL) of 10% of the Supply Contract Value is not availed by the contractor, then this 10% payment amount will be payable along with the point No A ii) along with the 70% payment milestone. ** The supply of Solar Modules & Inverters shall be scheduled in line with timelines for construction of transmission line. Any payment related to supplies will not be done by the employer till first 10 months of the award. In case transmission line gets ready, the timeline for payment against supplies will be reduced to 6 months. (iii) Ten percent (10%) payments shall be paid against successful erection, testing and commissioning of materials on pro rata basis at site. (iv) Final Ten percent (10%) payment of Supplies shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. B. The payment for the Service Portion of the Second Contract (Services Contract) shall be made as per the following terms and conditions. No Initial Advance Payment shall be made against the Service Portion Part. i) For Freight and Insurance Portion, the payment shall be made in line with Supply Portion of the Second Contract, as described in point A (ii) of this clause, without releasing any initial advance. The complete payment of the freight will be done along with the respective deliveries of the supply portion at site. ii) For Erection, Testing and Commissioning Portion, the payment shall be made as detailed below: - (a) Eighty Percent (80%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid on pro-rata basis on completion of installation of equipment on certification by the Engineer-In-Charge/ Project Manager for the quantum of work completed after successful clearance of quality check points involved in the quantum of work billed. (b) Ten Percent (10%) of the total price of Design, Engineering, Erection, Testing and Commissioning shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned. (c) Final Ten percent (10%) payment of Design, Engineering, Erection, Testing and Commissioning shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. iii) For Civil & Allied works portion, of the 1st contract, the payment shall be made as detailed below: (a) Eighty Percent (80%) of the total price of Civil Works shall be paid progressively on certification by the Project Manager/ Engineer In - Charge for the quantum of work completed/ Milestones achieved after successful clearance of quality check points involved in the quantum of work. (b) Ten Percent (10%) of the total price of Civil Works shall be paid against successful commissioning of the plant on pro rata basis for the capacity commissioned. (c) Final Ten percent (10%) payment of Civil Works shall be paid against submission of the BG of the equivalent amount & against the Operational Acceptance of the plant Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and O&M manual. This BG shall be valid for a period of 18 (Eighteen) months from the date of its issuance & will be released after CUF demonstration on completion of first year of O&M, pursuant to the submission of all requisite documentation up to the final acceptance of the Plant facilities. However, in case of any delay, the BG shall be extended suitably. C. For the Third Contract (related to Operation & Maintenance Part), the payment shall be made as detailed below: - (a) Operation and Maintenance of the entire Project payment will be released on quarterly basis at the end of every quarter for each year till 10 (Ten) years. (i) Year 1: OM -1 (ii) Year 2: OM -2 (iii) Year 3: OM -3 (iv) Year 4: OM -4 (v) Year 5: OM -5 (vi) Year 6: OM -6 (vii) Year 7: OM -7 (viii) Year 8: OM -8 (ix) Year 9: OM -9 (x) Year 10: OM -10 In case of any default, Non-Performance or breach of contractual conditions of the O&M contract during the O&M period, the penalties/deductions, if applicable will be liable to be deducted from the Quarterly O&M payments first & then from the Contract Performance Security. D. For the Fourth Contract (related to Acquisition & Transfer of Land/Leasing of Land), the payment shall be made as detailed below: - For the Acquisition & Transfer of Private land 1. Fifty Percent (50%) of the Land Cost Component of the Contract Price will be paid as under: (i) Acceptance of Notification of Award and Signing of the Contract Agreement. (ii) Submission of unconditional Bank Guarantees towards Contract Performance Securities. (iii) Submission of documents related to Land. (iv) Submission of application to State Nodal Agency for in-principle approval of state agency for availability of land or Acceptance of proposal/ application to State Nodal by state agency. (v) Successful completion of transfer of 50% of the total quantum of offered land on Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd and as per law for the same. 2. Balance Fifty Percent (50%) of the Land Cost Component of the Contract Price will be paid as under: (i) Fulfillment of Conditions mentioned at Clause D 1. (i), (ii), (iii), (iv), (v) above. (ii) Submission of documents related to Land. (iii) Submission of application to State Nodal Agency for in-principle approval of state agency for availability of land or Acceptance of proposal/ application to State Nodal by state agency. (iv) Successful completion of transfer of remaining 50% of the total quantum of offered land on Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd and as per law for the same. Notes: In case the contractor is not able to Successfully Transfer/Acquisition/Registration of Sale Deed in favor of SECI Ltd for the remaining quantum of offered land, even after the additional grace period of 03 months over & above the allocated time, then its Proportionate CPS will be encashed. For the leasing of Government/PSU/Private Land a) One Hundred Percent (100%) of the Land Cost Component of the Contract Price will be paid as under: (i) Acceptance of Notification of Award and Signing of the Contract Agreement. (ii) Submission of the Performance Security Bank Guarantee in respect of the Contract. (iii) Submission of copy of Allotment Letter of land issued by Competent Authority in favour of Bidder/Employer. (iv) 100 % Transfer of lease deed / sub-lease of land in favor of Solar Energy Corporation of India Limited, The above payment terms are applicable in case the Lease Deed charges are to be paid on total Lump sum basis. However, the prevailing Govt Regulations will prevail at the time of actual payment of the lease amount. E. All the payment shall be released from Owner’s Head Office, New Delhi upon submission of Original Documents like MDCC, delivery challan, warranty certificate, LR, WCC, MRN, commissioning certificate, handing over certificate, Insurance, PF, ESI, etc as required and mentioned against each Milestone payment, duly certified by the authorized representative of the Employer/Owner.
9 | Section VIII Schedule of Rates | Amendment 1 | Amendment 2 | Version Amendment 2 : Once again the Schedule of Rates or SOR has been updated. The New Excel format for the Schedule of Rates or SOR has been added, which comprises of Schedule Nos 1-5. Bidders are required to consider this revised SOR format only while filling up the price bid. Earlier SOR format during tendering or amendment 1 or any other format will not be considered for the purpose of evaluation & the bids shall be summarily rejected in case of old SOR format/Any other SOR format. | Version Amendment 3 : Void. The Ceiling limits for the EPC & O&M price are hereby removed & once again the Schedule of Rates or SOR has been updated. The New Excel format for the Schedule of Rates or SOR has been added, which comprises of Schedule Nos 1-5. Bidders are required to consider this revised SOR format only while filling up the price bid. Earlier SOR format during tendering or amendment 1 & 2 or any other format will not be considered for the purpose of evaluation & the bids shall be summarily rejected in case of old SOR format/Any other SOR format.
10 | Section I Invitation for Bids | Amendment 1 5 of 5 | Amendment 2 Add New Clause No 15 | Version Amendment 2 : Add New Clause No 15 EVALUATION OF FINANCIAL PART (SECOND ENVELOPE) pursuant to ITB 32.3 Add 02 new clauses 32.3.7 & 32.3.8 to the existing clause: 32.3.7 The Ceiling Limit of Quoted EPC Price including GST (The Total sum Schedule Nos 1,2 & 3) comprising of the total price of Schedule No. 1 Plant and Mandatory Spare Parts Supplied from Abroad+ Schedule No. 2. Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country + Schedule No. 3. Freight, Design, Civil & Installation and Other Services (Ex Works Supply of all Equipments and materials including mandatory spares and any other supplies specified in the tender Documents, providing all services i.e. Transportation for delivery at site and Insurance including unloading, storage, handling at site, Civil works, Erection, Installation, Testing and Commissioning, performance testing in respect of all the equipment’s supplied and any other services specified in the Tender Documents including Goods & Service Tax) excluding O&M : The Total Quoted EPC price under Cell No D8 of Schedule No 5 including GST shall not exceed INR 475 Crores (Indian Rupees Four hundred & seventy five Crores Only). After opening of the price bid, if it is found that the Quoted EPC price under Cell No D8 of Schedule No 5 including GST is more than INR 475 Crores Indian Rupees Four hundred & seventy five Crores Only), then the bid shall be summarily rejected being the non-responsive bid and the bidder shall not be shortlisted for participation in reverse auction. Bidders are required to quote the total EPC price including GST for the commercial, contractual and technical obligations outlined in the tender documents 32.3.8 The Ceiling Limit of Quoted NPV of O&M Price including GST for 10 years O&M period: The Quoted NPV of O&M Price including GST for total 10 years O&M period under Cell No D10 of Schedule No 5 shall not exceed INR 24 Crores (Indian Rupees Twenty Four Crores only). After opening of the price bid, if it is found that the Quoted NPV of O&M Price including GST under Cell No D10 of Schedule No 5 for total 10 years O&M period is more than INR 24 Crores (Indian Rupees Twenty Four Crores only), then the bid shall be summarily rejected being the non-responsive bid and the bidder shall not be shortlisted for participation in reverse auction. O & M Charges on Year on Year basis must be in equal or in ascending order only. | Version Amendment 3 : Void. The Ceiling limits for the EPC & O&M price are hereby removed.
11 | Section V Special Conditions of Contract | 6 of 12 | Amendment 1 | During the demonstration of yearly CUF, any shortfall from specified CUF shall attract the LD @ INR 3.5/kWh for each unit shortfall. The CUF shall be calculated as per the formula mentioned Section VII, Scope of Work and Technical Specifications | This clause is hereby removed. Kindly refer , Annexure 2 of the "Annexure G, O&M Agreement" for the calculations of the liquidated damages for shortfall in CUF.