## Amendment 03
Tender No. SECI/C&P/OP/17/007/2022-23
The Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 100 MW (AC) Floating Solar PV Project having 10 years plant O&M At Getalsud Dam, Ranchi, Jharkhand India
S. No. | Section | Page No. | Clause | Original Version | Amendment
1 | Specific Procurement Notice | 6 | 7 | All Bids must be accompanied by a Bid Security of the INR 6 Crores (Indian Rupees Six Crores only), or USD 1 Mn (US Dollars One Million only) as specified for the contract in case of a Bid Security. | All Bids must be accompanied by a Bid Security of the INR 1.5 Crores (Indian Rupees One & half Crores only), or USD 0.2 Mn (US Dollars Zero point Two Million only) as specified for the contract in case of a Bid Security.
2 | Section III – Evaluation and Qualification Criteria | 73 | 3.2 Average Annual Turnover | Minimum average annual turnover of INR 228 Crores (Indian Rupees Two hundred & Twenty-Eight Crores only) or USD 27 M (US Dollars Twenty-Seven Million only), calculated as total certified payments received for contracts in progress or completed within the last 03 (Three) years For Indian companies, other income (as per the Companies Act,2013 including amendment/ clarifications), shall not be considered for arriving at annual turnover | Minimum average annual turnover of INR 193 Crores (Indian Rupees One hundred & Ninety Three Crores only) or USD 23 M (US Dollars Twenty-Three Million only), calculated as total certified payments received for contracts in progress or completed within the last 03 (Three) years For Indian companies, other income (as per the Companies Act,2013 including amendment/ clarifications), shall not be considered for arriving at annual turnover
3 | Section III – Evaluation and Qualification Criteria | 74 | 3.3 Financial Resources | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets & lines of credit, other than any contractual advance payments to meet: (i) the following cash-flow requirement: INR 95 Crores (Indian Rupees Ninety-Five Crores only) or USD 11 M (US Dollars Eleven Million only) | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets & lines of credit, other than any contractual advance payments to meet: (i) the following cash-flow requirement: INR 75 Crores (Indian Rupees Seventy Five Crores only) or USD 9 M (US Dollars Nine Millions only)
4 | Section III – Evaluation and Qualification Criteria | 77 | 4.2(a) Specific Experience | Participation as contractor, joint venture member, management contractor, or subcontractor or Developer: Route I&II: (A) Must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, Supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), Installation and Commissioning of Grid connected Solar PV Power Plant(s) of total cumulative Capacity not less than 50 (Fifty) MW in last five years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND (B) The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), installation & commissioning of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW or above in last five years from last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission | Participation as contractor, joint venture member, management contractor, or subcontractor or Developer: Route I&II: (A) Must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, Supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), Installation and Commissioning of Grid connected Solar PV Power Plant(s) of total cumulative Capacity not less than 50 (Fifty) MW in last five years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND (B) The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), installation & commissioning of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 5 (Five) MW or above in last five years from last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission
5 | Appendix A to Section VII, Chapter – 3: Special Technical Conditions | 168 of 309 | Cl. No. 3. Specific Requirements; Sl. No. 2 | Maximum block size for the FSPV plant shall not be higher than 5 MW (AC). Blocks shall be symmetrical in shape. | There is no restriction on the maximum block size however it should be symmetrical. And all such block size will be mutually finalized during Design phase with due consent of SECI.

## Clarifications to the Queries
The Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 100 MW (AC) Floating Solar PV Project having 10 years plant O&M At Getalsud Dam, Ranchi, Jharkhand India
SECI/C&P/OP/17/007/2022-23
S. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Queries | Clarifications
1 | Annexure I Available Reservoir Area with Contour Details and Amendment 1 - Point no. 11 | - | Maximum Permissible Plant Area and Point no. 11 | Total Available Area - 418 Ha. Approx. Maximum permissible plant area - 172 Ha. And Maximum block size for the FSPV plant shall not be higher than 5 MW (AC). Blocks shall be symmetrical in shape. | 1. Bidder understands that over given 418 Ha of total available area, bidder is free to choose any 172 Ha for the plant area. Please clarify. 2. As per the layout working carried out in co-ordination with the float vendors, the maximum MWp capacity that can be accommodated over 172 Ha. is approx. 92 MWp (subjective to the restriction of maximum block size not higher than 5 MW (AC)) but to meet the minimum tender requirement of 126 MWp usable area requirement shall be 240 Ha Approx. (additional water body area required is of 68 Ha.) 3. If the bidder is free to select the block size, then the maximum area requirement to meet 126 MWp can be brought down to 200 Ha. (additional water body area required is of 28 Ha.) So we request SECI to relax the restriction of maximum permissible plant area to 240 Ha or allow the bidder to design the block size and relax the restriction of maximum permissible plant area to 200 Ha. Please accept. | Maximum permissible plant area should not exceed 10% of average water surface area of the reservoir which is 1870.7 ha. As per the Water Lease Agreement, area covered by floats should be restricted to 172Ha but the Total Area including the Float Boundary is 221Ha (i.e. 11.05Ha X 20) Kindly refer Amendment 01.
2 | ESIA_Getalsud_R1 released on Amendment 2 | 168 of 262 | 11.3.1 - Water |  | Bidder understands that the minimum water level in the reservoir mentioned in this clause is referred to the MDDL (Minimum Draw Down Level) of the reservoir mentioned in the tender which is 584.30 MSL and the Contractor shall only work if the water level in the reservoir is above the MDDL. Please confirm. Also, bidder understands that if any suspension of work happens due to the water level of the reservoir goes below the MDDL as mentioned in this clause, the Contractor shall be eligible for extension of time (EoT), equivalent to such suspension. | It is confirmed that the understanding of the contractor is correct. The water level is controlled by the Water Resources Department, GoJ, and is beyond the control of SECI/EPC Agency. However, this is an operational concern, and the EPC Agency is required to inform SECI and WRD in time in case MDDL is not maintained. If any suspension of Work occurs due to Force Majeure like Water Level going below MDDL, Time Extension shall be accorded.
3 | ESIA_Getalsud_R1 released on Amendment 2 | 182 of 262 | 11.3.2 - Water |  | Maintaining the min. water level at the reservoir is beyond the control of the Contractor as the Contractor does not have any authority to control the gates of the reservoir or flow of the incoming water. Hence, we understand that the scope of maintaining the min. water level at the reservoir shall not be in scope of Contractor during construction/ O&M period. | Water Level is controlled by the Water Resources Department, GoJ and is beyond the control of SECI/ EPC Agency. However, this is an operational concern, and the EPC Agency is required to inform SECI and WRD in time in case MDDL is not maintained.
4 | ESIA_Getalsud_R1 released on Amendment 2 | 174 of 262 | 11.3.1 - Ecology |  | Monitoring the oxygen content of the water where the PV arrays are populated can be considered under bidder scope. However, maintaining the oxygen content can be excluded from bidder's scope. Please accept. | 1. Regular monitoring: a. EPC at OMS stage can set up a joint monitoring cell with WRD and carry out water quality testing at set intervals (say, 90 days) from a government accredited lab and in case any values are found out of the range, EPC shall inform the monitoring cell & SECI and further mitigation measures shall be taken by SECI in consultation with WRD. b. Any (construction) waste needs to be removed promptly as it will obstruct penetration of light and aeration of water. 2. Mitigation Measures: After regular monitoring, if the DO levels are found to be low, then aerators can be used. Such measures are not in the scope of EPC and if required, SECI in consultation with the WRD will deploy these Aerators based on the requirement.
5 | ESIA_Getalsud_R1 released on Amendment 2 | 215 of 262 | Employment | As per the policy, contractor to give preference to local population in matters of employment. | Bidder understands that the engagement of local population or giving employment is not mandatory for the Contractor, however the contractor shall give preference to the local population as per its requirement. Please confirm. | Engagement of local population or giving employment is not mandatory. However the EPC agency shall give preference to the local population as per the requirements.
6 | RAP_Report__100 MW Floating Solar PV Project at Getalsud, Jharkhand | 77 of 138 | 6.3 - E. Loss of Livelihood |  | Bidder understands that the engagement of local population or giving employment is not mandatory for the Contractor, however the contractor shall give preference to the local population as per its requirement. Please confirm. | Engagement of local population or giving employment is not mandatory. However the EPC agency shall give preference to the local population as per the requirements.
7 | Section VIII – General Conditions of Contract | 215 of 365 | 10. Employer’s Responsibilities | 10.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the Appendix to the Contract Agreement titled Scope of Works and Supply by the Employer. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix 10.7 All costs and expenses involved in the performance of the obligations under this GCC Clause 10 shall be the responsibility of the Employer, save those to be incurred by the Contractor with respect to the performance of Guarantee Tests, in accordance with GCC Sub- Clause 25.2. | Kindly confirm that the Employer shall give full possession of and accord all rights of unencumbered access to the Reservoir and associated Land for Main Control Room, Switchyard, Float Assembly Area on or before the date of Effective Date also request Employer to take care of any local issues arising out of the possession of and accord all rights of unencumbered access to the Reservoir and associated Land for Main Control Room, Switchyard, Float Assembly Area, Float launch pad etc during the currency of the contract. In case of any delay in the grant of the site/ access to the contractor or delay in execution due to any local issues then due EOT and compensation for the additional cost would be granted by the employer. | Employer will give full possession of and accord all rights of unencumbered access to the Reservoir and associated Land for Sub-station. The float assembly area has to be arranged by the EPC agency. In case of hindrance due to local issues, same has to be communicated to the employer immediately. However in case if the overall Project timelines are delayed on account of such hindrances, which is well substantiated and validated based on factual evidences, then suitable time extension may be granted by SECI for all such reported hindrances. However, the contractor should endeavor to resolve all such site issues/hindrances first hand & in case of non resolution only, time extension case may be considered, for the cases as elaborated above. SECI will facilitate and align the land required for the launching pad with WRD. Such launching pad as identified by the contractor during the execution stage will be offered to SECI and based on the feasibility and consent of WRD, SECI will facilitate all possible efforts, approval and clearances required for such launching Pad. SECI will play active role in finding and facilitating such feasible launching pad in collaboration with the Contractor. The access road coordinates lies at the vacant area available opposite to the proposed sub-station, which is also alongside the discussed feasible cable laying route. The tentative area is marked as "A" in the attached drawing No as drwg/proposed/1
8 | Specific Procurement Notice | 6 | 7 | All Bids must be accompanied by a Bid Security of the INR 6 Crores (Indian Rupees Six Crores only), or USD 1 Mn (US Dollars One Million only) as specified for the contract in case of a Bid Security. | Kindly reduce the Bid Security amount Rs. 6 Cr. To Rs. 3 Cr | Kindly refer to Amendment 03.
9 | Section III – Evaluation and Qualification Criteria | 73 | 3.2 Average Annual Turnover | Minimum average annual turnover of INR 228 Crores (Indian Rupees Two hundred & Twenty-Eight Crores only) or USD 27 M (US Dollars Twenty-Seven Million only), calculated as total certified payments received for contracts in progress or completed within the last 03 (Three) years For Indian companies, other income (as per the Companies Act,2013 including amendment/ clarifications), shall not be considered for arriving at annual turnover | Minimum average annual turnover of INR 193 Crores for last 3 financial years (i.e. FY 2020-21, 2021-22 and 2022-23) Also, we have working capital Rs. 308.64 Cr. of last Financial year (i.e. 2022-2023) | Kindly refer to Amendment 03.
10 | Section III – Evaluation and Qualification Criteria | 77 | 4.2(a) Specific Experience | Participation as contractor, joint venture member, management contractor, or subcontractor or Developer: Route I&II: (A) Must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, Supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), Installation and Commissioning of Grid connected Solar PV Power Plant(s) of total cumulative Capacity not less than 50 (Fifty) MW in last five years as on last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission. AND (B) The bidder must have experience in EPC execution of Ground mounted Solar Projects on Turnkey basis including Design, supply (Supply of Modules & Inverters can be inclusive or exclusive in the bidder’s scope in the past experience), installation & commissioning of at least 02 (Two) Grid connected Solar PV Power Plant Projects having an individual capacity of 10 (Ten) MW or above in last five years from last date of bid submission. However, such Grid connected Solar PV Power Plant capacity must have been in satisfactory operation for at least six (06) months prior to the last date of bid submission | We request you to please allow two project of 5-5 MW each for meeting the specific criteria as per tender requirement. | Kindly refer to Amendment 03.
11 | Section -III and Amendment-1 | 78 of 365 | 3.3 Financial Resources | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets & lines of credit, other than any contractual advance payments to meet: (i) the following cash-flow requirement: INR 93 Crores | We (The Bidder) request the Employer to please reduce cash-flow requirement (the availability of financial resources such as liquid assets & lines of credit) from INR 93 Crores to INR 50 Crores | Kindly refer to Amendment 03.
12 | Section -II | 58 of 365 | ITB 20.1 | The amount and currency of the Bid Security shall be 6 Cr (Indian Rupees Six Crores only) or USD 1 Mn (US Dollars One Million only) | We (The Bidder) request the Employer to please reduce EMD Bid Security for further Rs.1.5 Crores | Kindly refer to Amendment 03.