## Amendment I
NIT No: SECI/C&P/NIT/2018/SCCL150
Tender for Design, Engineering, Supply, Construction, Notice Inviting Tender For Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 129 MW (AC) Solar PV Power Plant under Domestic Competitive Bidding atSingareni Collieries Company Limited (SCCL), Telangana
Sl. No. | Section | Page No. | Clause | Original Version | Amendment | Justification
1 | General | - | - | 'Pedapally' | 'Pedapally' shall be replaced by 'Ramagundam'
2 | General | - | - | 'Pegadapally' | 'Pegadapally' shall be replaced by 'STPP'
3 | General | - | - | 'TSTRANSCO' | 'TSTRANSCO' shall be replaced by 'TSTRANSCO/TSNPDCL'
4 | General | - | - | 'Annexure-B (PG Test Procedure)' | 'Annexure-B (PG Test Procedure)' shall be replaced by 'Annexure-C (PG Test Procedure)'.
5 | General | - | - | 'Approved makes' | 'Approved makes' shall be replaced by 'Reputed makes'.
6 | Scope of Work | 2 of 11 | 1.1 | Project Particulars | Kindly refer Annexure-I to Amendment-1.
7 | Scope of Work | 4 of 11 | 4.1.1 | Adequate capacity of Solar PV modules of suitable rating including module mounting structures (fixed tilt), fasteners, suitable MMS foundations and module interconnections. | Adequate capacity of Solar PV modules of suitable rating including module mounting structures (seasonal tilt), fasteners, suitable MMS foundations and module interconnections.
8 | Scope of Work | 5 of 11 | 4.1.19 | Spares & consumables, as required or recommended, for the complete O&M period. | Spares & consumables, as required or recommended, for comprehensive O&M
9 | Scope of Work | 6 of 11 | 5.1.3 | Construction and erection of perimeter fence/ boundary wall and main/ security gate(s). | VOID
10 | Scope of Work | 8 of 11 | 6.3 | Gate entry system, as per requirement, shall be followed by the contractor for all their personnel and vehicle movement. | Gate entry system, as per SCCL requirement, shall be followed by the contractor for all their personnel and vehicle movement.
11 | Scope of Work | 8 of 11 | 7.1 | Total Operation & Maintenance of the SPV Plant shall be with the Contractor, after commissioning / operational acceptance of the plant till final acceptance or culmination of the O&M period, whichever is later, shall include deployment of engineering personnel, technicians and security personnel. | Total Operation & Maintenance of the SPV Plant shall be with the Contractor, after operational acceptance of the plant till culmination of the O&M period, shall include deployment of engineering personnel, technicians and security personnel.
12 | Scope of Work | 10 of 11 | 8.2 | Daily work of the operation and maintenance in the Solar Photovoltaic Power Plant involves periodic cleaning of Modules, logging the voltage, current,… | Daily work of the operation and maintenance in the Solar Photovoltaic Power Plant involves periodic cleaning of Modules including periodic tilt angle change as and when required, logging the voltage, current,…
13 | Technical Specifications | 7 of 136 | 2.1 | The work execution planning for supply, erection, commissioning and all other allied works for SPV Power Plant shall be such that it is completed within stipulated time from the date of order/ LOI/ NTP | The Project work execution planning for supply, erection, commissioning and all other allied works for SPV Power Plant shall be such that it is commissioned within stipulated time from the date of order/ LOI/ NTP, whichever is later.
14 | Technical Specifications | 8 of 136 | 1.2 | Technical Requirements | Kindly refer Annexure-II to Amendment-1.
15 | Technical Specifications | 9 of 136 | 1.3.1 | The glass used to make PV Modules shall be toughened low iron glass with minimum thickness of 4.0 mm. The glass shall have transmittance of above 90%. | The glass used to make PV modules shall be toughened low iron glass with transmittance above 90%. The minimum thickness of mono or multi crystalline modules shall be 4.0 mm for 72 cell module and 3.2 mm for 60 cell module. In case of glass-glass Modules, glass thickness on each side shall be minimum of 2 mm.
16 | Technical Specifications | 53 of 136 | 15.6.3 | In the case of SMBs (String Monitoring Boxes), separate electronic earth pit, isolated from electrical/structure earth shall be provided for each SMB (or one for nearby SMBs) to connect RS485 shield inside each SMB | VOID
17 | Technical Specifications | 83 of 136 | 20.4.1 | LED luminaires' parameters | Kindly refer Annexure-III to Amendment-1.
18 | Technical Specifications | 87 of 136 | 22.1 | CCTV Cameras along with monitoring stations (sufficient numbers) and all other accessories required for its proper operation must be installed to have complete coverage of following areas for 24 hours. (i) Main entry: Covering all the entry/exit (ii) Along the Plant Perimeter: Covering complete perimeter of Plant Area to capture all possible intrusion (iii) Control Rooms: Covering Entry/Exit and activities within Control Rooms The Contractor has to propose the locations and number of cameras required for the Plant during bidding, however Employer’s decision on number of cameras shall be final. | CCTV Cameras along with monitoring stations (sufficient numbers) and all other accessories required for its proper operation must be installed to have complete coverage of following areas for 24 hours. (i) Main entry: Covering all the entry/exit (ii) Along the Plant Perimeter: Covering complete perimeter of Plant Area to capture all possible intrusion (iii) Control Rooms: Covering Entry/Exit and Equipment Rooms (iv) Switchyard
19 | Technical Specifications | 101 of 136 | 31.3 | (i) Topping: wearing course of 20 mm thick pre-mix carpet or surface dressing, compacted 75mm thick, with murrum blended with WBM Grade-III, as applicable. | (i) Topping: wearing course of 20 mm thick pre-mix carpet (for approach road) or surface dressing, compacted 75mm thick, with murrum blended with WBM Grade-III (for internal roads).
20 | Technical Specifications | 115 of 136 | 38.25 | Modules shall be clamped & bolted with the structure properly. The material of clamps shall be Al / SS – 316 having weather resistant properties. Clamp/bolt shall use EPDM rubber and shall be designed in such a way so as not to cast any shadow on the active part of a module. | Modules shall be clamped or bolted with the structure properly. The material of clamps shall be Al / SS – 316 having weather resistant properties. Clamp/bolt shall use EPDM rubber and shall be designed in such a way so as not to cast any shadow on the active part of a module.
21 | Technical Specifications | 117 of 136 | 41.2.1 | Air-conditioned area (with provision of split A/C unit of adequate capacity) for SCADA room (min. carpet area 12m2) & Conference room (min. carpet area 20 m2) | Air-conditioned area (with provision of split A/C unit of adequate capacity) for SCADA room (min. carpet area 12m2), Conference room (min. carpet area 20 m2) & Supervisor cabin and office area (min. carpet area 20 m2)
22 | Technical Specifications | 125 of 136 | 56.6 | The septic shall be designed as liquid retaining structure conforming to IS:3370 for design loads as specified under Cl. No.55. | The septic tank shall be designed as liquid retaining structure conforming to IS:3370 for design loads as specified under Cl. No. 35.
23 | Annexure-C (PG Test Procedure) | 9 of 11 | 2.2 | Capacity Utilization Factor for Solar Plant shall be calculated as per the following formula. CUF=E_ac/(8760×P_ac×(1-DF×N) ) where, Eac is the number of units recorded in the plant end ABT meter, kWh 8760 refers to the number of hours in non-leap year. It shall be replaced by 8784 hours during leap year Pac is the plant AC capacity, kW DF is module degradation factor, 0.7% per year N is the number of years of operation after operational acceptance of the plant CUF shall be calculated on annual basis from the date of operational acceptance of the plant till the end of O&M period. | Capacity Utilization Factor for Solar Plant shall be calculated as per the following formula. CUF=E_ac/{8760×P_ac×[1-DF×(N-1)]} where, Eac is the number of units recorded in the plant end ABT meter excluding auxiliary consumption, kWh 8760 refers to the number of hours in non-leap year. It shall be replaced by 8784 hours during leap year Pac is the plant AC capacity, kW DF is module degradation factor, 0.7% per year N is the number of years of operation after operational acceptance of the plant CUF shall be calculated on annual basis from the date of operational acceptance of the plant till the end of O&M period. Module degradation factor will not be considered for first year CUF calculation. It is the Contactor’s responsibility to envisage and install extra DC capacity to accommodate any degradation during first year. 0.7% per year will be considered from second year of operation.
24 | Special Technical Specifications | 2 of 13 | 2.1 | Electrical Interconnection Details Distance to connecting substation: 6000 m (approx.) | Electrical Interconnection Details Distance to connecting substation: 8000 m (approx.)
25 | Special Technical Specifications | 5 of 13 | 6.1 | The 50MW Solar Power is planned to be installed at the land parcel available in the vicinity of the Singareni OC Mines under the RG – III area on Pedapalli – Manthani Road. | The 50MW Solar Power is planned to be installed at the land parcel available in the vicinity of the Singareni OC Mines under the RG – III area on Centenary colony- Godavarikhani Coal Corridor Road.
26 | Special Technical Specifications | 8 of 13 | 12.1 | Electrical Interconnection Details Distance to connecting substation: 1500 m (approx.) | Electrical Interconnection Details Distance to connecting substation: 3000 m (approx.)
27 | Special Technical Specifications | 8 of 13 | 12.1 | Access Nearest Railway Station: Bhadadri Kothagudem | Access Nearest Railway Station: Manuguru
28 | Special Technical Specifications | 11 of 13 | 17.1 | Electrical Interconnection Details Substation Details: 33/3.3kV SCCL Auxiliary S/s Distance to connecting substation: 200 m (approx.) | Electrical Interconnection Details Substation Details: 33/3.3kV SCCL Indaram Khani UG Mine Substation Distance to connecting substation: 10,000 m (approx.)
29 | Special Technical Specifications | 13 of 13 | 19.1 | The power thus generated from the solar power plant is required to be evacuated at 33kV voltage level to the nearby 33/ 3.3kV substation through a 33kV UG cable. | The power thus generated from the solar power plant is required to be evacuated at 33 kV voltage level to 33/3.3 kV SCCL Indaram Khani UG Mine Substation through a 33 KV OHT line.
30 | Scope of Works | 3 of 11 | 2 | S.No. Site Details Site Capacity (MW) Locations 1 Site-1 60 (50+10) Yellandu Area | S.No. Site Details Site Capacity (MW) Locations 1 Site-1 39 Yellandu Area
31 | Special Technical Specifications | 2 of 13 | 2.1 | Proposed capacity of the solar power plants: 60 MW (50MW + 10MW) | Proposed capacity of the solar power plants: 39 MW
32 | Special Technical Specifications | 4 of 13 | 4.1 | Based on the TS regulations for power evacuation, the said capacity of 60MW is divided into 50MW and 10MW suiting best to fit in the area available. | VOID
33 | Special Technical Specifications | 4 of 13 | 4.2 | The power thus generated from the 50MW solar power plant is required to be evacuated at 132kV voltage level to the nearby 132/33kV NPDCL sub-station (Yellandu) through 132kV transmission lines. However, for the balance 10MW capacity, the power is required to be evacuated at 33kV to the nearest substation through transmission line. | The power thus generated from the 39 MW solar power plant is required to be evacuated at 132kV voltage level to the nearby 132/33kV NPDCL sub-station (Yellandu) through 132kV transmission lines.
34 | Technical Specifications | 10 of 136 | 1.4.1 | PV modules must be warranted with linear degradation rate of power output except for first year (maximum 2.5% including LID) and shall guarantee 80% of the initial rated power output at the end of 25 years. | PV modules must be warranted with linear degradation rate of power output except for first year (maximum 3% including LID) and shall guarantee 80% of the initial rated power output at the end of 25 years.
35 | Annexure-A (PV Module PDI Protocol) | New Addition |  |  | Attached with the Amendment 1
36 | Annexure-B (Civil FQP) | New Addition |  |  | Attached with the Amendment 1
37 | General | - | - | Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 150 MW (AC) Solar PV Power Plant under Domestic Competitive Bidding at Singareni Collieries Company Limited (SCCL), Telangana | The total cumulative Project capacity has been revised to 129 MW (AC). Accordingly, the Project will be now determined as "Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 129 MW (AC) Solar PV Power Plant under Domestic Competitive Bidding at Singareni Collieries Company Limited (SCCL), Telangana" This revised cumulative capacity of 129 MW (AC) will supersede any other cumulative capacity mentioned anywhere in the tender document. The revised bifurcation of site capacities is mentioned in the subsequent Amendment below. | Project owner, SCCL has reduced the total Project capacity and the revised capacity is 129 MW (AC). As per owner's requirement.
38 | General | - | - | - | Total Revised cumulative capacity = 129 MW (AC) Total No of Sites = 4 (Four) Nos including YELLANDU AREA, RAMAGUNDAM –III AREA, MANUGURU AREA, STPP AREA Bidders are required to consider the revised cumulative capacity and revised No of sites only while bidding, which is also mentioned in the table below. This revised cumulative capacity of 129 MW (AC) & revised 04 sites will supersede any other cumulative capacity and total No of sites mentioned anywhere in the tender document. Bidders are required to bid accordingly. | Project owner, SCCL has reduced the total Project capacity and the revised capacity is 129 MW (AC). As per owner's requirement.
39 | IFB | - | - |  |  | Project owner, SCCL has reduced the total Project capacity and the revised capacity is 129 MW (AC). As per owner's requirement.
40 | Invitation for Bids (IFB) | 2 of 10 | - | ELIGIBILITY CONDITIONS SET FORTH IN THE TENDER DOCUMENT ARE AS PER 150 MW (AC) CUMULATIVE CAPACITY BASIS ONLY. BIDDERS ARE REQUIRED TO QUOTE ACCORDINGLY FOR THE COMPLETE CUMULATIVE CAPACITY OF 150 MW (AC). THE TOTAL CAPACITY OF 150 MW WILL BE AWARDED TO A SINGLE SUCCESSFUL BIDDERS ONLY SELECTED AFTER E-RA ON INDIVIDUAL SITE BASIS. THE TOTAL PRICE OF EPC AND O&M ARRIVED AFTER E-RA, WILL BE CONVERTED TO THE PER MW PRICE. BASED ON THE PER MW PRICE ARRIVED, THE PER SITE PROJECT EPC AND O&M PRICE WILL BE CALCULATED BY MULTIPLYING THE PER MW PRICE WITH THE RESPECTIVE SITE CAPACITY. IN THE SAME WAY, THE RESPECTIVE SITE O&M PRICES WILL BE CALCULATED. ACCORDINGLY, 05 DIFFERENT EPC AND O&M NOA/CONTRACT AGREEMENT WILL BE RELEASED FOR THE RESPECTIVE SITE BY THE OWNER. EMD CAN BE SUBMITTED BY THE BIDDERS JOINTLY FOR THE COMPLETE 150 MW PROJECT CAPACITY. HOWEVER, THE SUCCESSFUL BIDDER WILL BE REQUIRED TO SUBMIT RESPECTIVE SEPARATE CONTRACT PERFORMANCE SECURITIES & ADVANCE BANK GUARANTEES (IF AVAILED) FOR INDIVIDUAL SITES AS THERE WILL BE INDIVIDUAL CONTRACT AGREEMENTS BASED ON SITE CAPACITY. OWNER RESERVES THE OPTION TO REDUCE ANY OF THE ABOVE-MENTIONED SITE CAPACITY FROM THE OVERALL CUMULATIVE CAPACITY BEFORE/AFTER AWARD OF CONTRACT AGREEMENT. ACCORDINGLY, THE TOTAL PROJECT PRICE WILL BE PROPORTIONATELY REDUCED & THE FINAL PROJECT PRICE ARRIVED AS SUCH AFTER REDUCTION WILL BE THE FINAL PROJECT PRICE OF THE CONTRACT AGREEMENT. | ELIGIBILITY CONDITIONS SET FORTH IN THE TENDER DOCUMENT ARE AS PER 129 MW (AC) CUMULATIVE CAPACITY BASIS ONLY. BIDDERS ARE REQUIRED TO QUOTE ACCORDINGLY FOR THE COMPLETE CUMULATIVE CAPACITY OF 129 MW (AC). THE TOTAL CAPACITY OF 129 MW WILL BE AWARDED TO A SINGLE SUCCESSFUL BIDDER ONLY SELECTED AFTER E-RA.HOWEVER, THERE WILL BE SEPARATE CONTRACT AGREEMENTS BASED ON SEPARATE SITES WITH THE SAME SUCCESSFUL BIDDER. E-RA WILL BE DONE ON THE TOTAL CUMULATIVE CAPACITY OF 129 MW ONLY. THE TOTAL PRICE OF EPC AND O&M ARRIVED AFTER E-RA, WILL BE CONVERTED TO THE PER MW PRICE. BASED ON THE PER MW PRICE ARRIVED, THE PER SITE PROJECT EPC AND O&M PRICE WILL BE CALCULATED BY MULTIPLYING THE PER MW PRICE WITH THE RESPECTIVE SITE CAPACITY. IN THE SAME WAY, THE RESPECTIVE SITE O&M PRICES WILL BE CALCULATED. ACCORDINGLY, 04 DIFFERENT EPC AND O&M NOA/CONTRACT AGREEMENT WILL BE RELEASED FOR THE RESPECTIVE SITE BY THE OWNER TO THE SINGLE SUCCESSFUL BIDDER ONLY. EMD CAN BE SUBMITTED BY THE BIDDERS JOINTLY FOR THE COMPLETE 129 MW PROJECT CAPACITY. HOWEVER, THE SUCCESSFUL BIDDER WILL BE REQUIRED TO SUBMIT RESPECTIVE SEPARATE CONTRACT PERFORMANCE SECURITIES & ADVANCE BANK GUARANTEES (IF AVAILED) FOR INDIVIDUAL SITES AS THERE WILL BE INDIVIDUAL CONTRACT AGREEMENTS WITH THE SUCCESSFUL BIDDER BASED ON SITE CAPACITY. OWNER RESERVES THE OPTION TO REDUCE ANY OF THE ABOVE-MENTIONED SITE CAPACITY FROM THE OVERALL CUMULATIVE CAPACITY BEFORE/AFTER AWARD OF CONTRACT AGREEMENT. ACCORDINGLY, THE TOTAL PROJECT PRICE WILL BE PROPORTIONATELY REDUCED & THE FINAL PROJECT PRICE ARRIVED AS SUCH AFTER REDUCTION WILL BE THE FINAL PROJECT PRICE OF THE CONTRACT AGREEMENT. | Clause clarified as per the requirement and better understanding of prospective bidders.
41 | Invitation for Bids (IFB) | 8 of 10 | Point (F) of Bid Information sheet | TENDER PROCESSING FEE : Amount: INR 46,90,500/- (Indian Rupees Forty Six Lacs & Ninety thousand and Five hundred only) inclusive of GST @ 18% | TENDER PROCESSING FEE : Amount: INR 25000/- (Indian Rupees Twenty Five Thousand only) inclusive of GST @ 18% | Management approval has been obtained for considering the minimal possible amount of Bid Processing Fee, so that it is not acting as a deterrent in the participation of bidders. Similar Bid Processing Fees has been proposed in the SECI Procurement Policy.
42 | instruction to bidders (ITB) | 24 of 46 | 32.4.1 (e) | Billing Break-up (BBU): • The successful bidder will be mandatorily required to provide the detailed Billing break up (BBU) with GST in line with SOR 1 & 2 at the time of Award of Contract Agreement. Same will form the part of Contract Agreement (CA) • For each item of SOR 1 & 2, the BBU shall be prepared in the same SOR format (Item name, UoM, Quantity, unit Ex Works price, GST, Total price etc) and the sum of all billing break-up item prices shall be equivalent to the each respective SORs item price with discounted rate of e-Reverse auction (If applicable). • The Contractor would be required to provide detailed Bill of Quantity (BOQ) along with the break-up of Contract Price (including taxes) and HSN code of the respective goods/services, at the time of signing of Contract Agreement which should match with the Price Quoted by the Contractor in its Price Bids and accepted by the Employer. This will be used by the Owner at the time of payment to the Contractor. Accordingly, bidders should diligently quote the taxes in the bid. • Owner shall reimburse the amount of taxes as per the rates mentioned by Contractor in the detailed BOQ. In case of any statutory variation in GST during the currency of the Contract, same will be reimbursed to the Contractor subject to the statutory variation clause of the Bidding document, only in respect of the items/quantity which have been mentioned by the Contractor in the detailed BOQ. • If there is difference in HSN/SAC classification and corresponding rate of GST of an item as confirmed/deemed confirmed by the bidder in its bid/detailed BOQ and HSN/SAC and corresponding rate of GST as interpreted under any interpretation/ judgment/ Notification/ Circular issued under the GST law before the award of contract, GST reimbursable to the bidder/Bidder shall be lower of the GST applicable at the rate as confirmed/deemed confirmed in the bid or actual GST paid/payable by the bidder for that item. • In case of imported Equipment/items purchased from third party (Bought-Out Items) are supplied to the Employer/Owner in execution of the Project, the price of such Goods shall be inclusive of all cost as well as any duties paid/payable in relation to import/purchase of such goods (viz., customs duties, GST & levies etc.) considering and taking into account the ITC as may be available under the applicable laws including GST. • In case of any statutory variation in GST during the currency of the Contract, same will be reimbursed to the Contractor only in respect of the taxes which are levied during the direct transaction held between Owner and the Contractor. Any statutory variation applicable in respect of the items/services procurement between third party/sub-contractor and the Contractor would not be reimbursed by Owner. The successful bidder will be required to provide the detailed Billing break up (BBU) with GST in line with SOR’s at the time of Award of Contract Agreement. Same will form the part of Contra t Agreement (CA) | Billing Break-up (BBU): • The successful bidder will be mandatorily required to provide the detailed Billing break up (BBU) with GST in line with SOR 1 & 2 at the time of Award of Contract Agreement. Same will form the part of Contract Agreement (CA) • For each item of SOR 1 & 2, the BBU shall be prepared in the same SOR format (Item name, UoM, Quantity, unit Ex Works price, GST, Total price etc) and the sum of all billing break-up item prices shall be equivalent to the each respective SORs item price with discounted rate of e-Reverse auction (If applicable). • The Contractor would be required to provide detailed Bill of Quantity (BOQ) along with the break-up of Contract Price (including taxes) and HSN code of the respective goods/services, at the time of signing of Contract Agreement which should match with the Price Quoted by the Contractor in its Price Bids and accepted by the Employer. This will be used by the Owner at the time of payment to the Contractor. Accordingly, bidders should diligently quote the taxes in the bid. • Owner shall reimburse the amount of taxes as per the rates mentioned by Contractor in the detailed BOQ. In case of any statutory variation in GST during the currency of the Contract, same will be reimbursed to the Contractor subject to the statutory variation clause of the Bidding document, only in respect of the items/quantity which have been mentioned by the Contractor in the detailed BOQ. • In case of imported Equipment/items purchased from third party (Bought-Out Items) are supplied to the Employer/Owner in execution of the Project, the price of such Goods shall be inclusive of all cost as well as any duties paid/payable in relation to import/purchase of such goods (viz., customs duties, GST & levies etc.) considering and taking into account the ITC as may be available under the applicable laws including GST. • In case of any statutory variation in GST during the currency of the Contract, same will be reimbursed to the Contractor only in respect of the taxes which are levied during the direct transaction held between Owner and the Contractor. Any statutory variation applicable in respect of the items/services procurement between third party/sub-contractor and the Contractor would not be reimbursed by Owner. The successful bidder will be required to provide the detailed Billing break up (BBU) with GST in line with SOR’s at the time of Award of Contract Agreement. Same will form the part of Contra t Agreement (CA) For First contract: In case of any clarification from the GST authorities on the interpretation of applicable GST rate during the contract period, revised GST will be considered for reimbursement of taxes and also taxes will be paid on actual basis as reported in GSTR-2A. Bidder should invoice separately for Equipments, machinery, solar panels and any other supply of goods involved in this contract mentioning their description of goods, HSN,value etc., For Second contract: In case of any clarification from the GST authorities on the interpretation of applicable GST rate during the contract period, revised GST will be considered for reimbursement of taxes and also taxes will be paid on actual basis as reported in GSTR-2A. Bidder should invoice separately for components, spare parts etc., consumed for O&M service involved in this contract mentioning their description of goods, HSN, value etc., | Clause amended as per the GST opinion sent by Owner for incorporation. As per owner's requirement.
43 | General Conditions of Contract (GCC) | 37 of 72 | 45.4.3 | Any complaint related to unserviceability/improper functioning of any & all component of the plant including but not limited to PV Module, PCU, Transformers, switchgears, SCADA, roads, drainage, water supply lighting system, office infrastructure, CCTV system should be immediately attended & rectified. If such complaint is not rectified within 48 hours from logging of complaint, Owner may choose to rectify the same through any other agency at the risk of Contractor and Owner shall recover 110% of such cost incurred from subsequent payment to the contractor. | Void | Clause found not suitable in line with the Tender.
44 | General Conditions of Contract (GCC) | 40 of 72 | 50.2 | During monsoon and other period, it shall be the responsibility of the Contractor to keep the construction work site free from water at his own cost. | During monsoon and other period, it shall be the responsibility of the Contractor to keep the construction work site & plant during O& M free from water at his own cost. | Suitable changes has been made in the existing clause to cover the O&M period also
45 | General Conditions of Contract (GCC) | 48 of 72 | 69.1 | If it shall appear to the Engineer-in-Charge/Project Manager that any work has been executed with unsound, imperfect or unskilled workmanship, or with materials of any inferior description, or that any materials or articles provided by the Contractor for the execution of the Work are unsound, or of a quality inferior to that contracted for, or otherwise not in accordance with the Contract, the Contractor shall on demand in writing from the Engineer-in-Charge/Project Manager or his authorized representative specifying the Work, materials or articles complained of notwithstanding that the same may have been inadvertently passed, certified and paid for, forthwith rectify or remove and reconstruct the Work so specified and provide other proper and suitable materials or articles at his own cost. In the case of any such failure the Engineer-in-Charge/Project Manager may on expiry of notice period rectify or remove and re-execute the Work or remove and replaced with others, the materials or articles complained of to as the case may be at the risk and expense in all respects of the Contractor. The decision of the Engineer-in-Charge/Project Manager as to any question arising under this clause shall be final and conclusive. | If, against documentary proofs, is established that any work has been executed with unsound, imperfect or unskilled workmanship, or with materials of any inferior description, or that any materials or articles provided by the Contractor for the execution of the Work are unsound, or of a quality inferior to that contracted for, or otherwise not in accordance with the Contract, the Contractor shall on demand in writing from the Engineer-in-Charge/Project Manager or his authorized representative specifying the Work, materials or articles complained of notwithstanding that the same may have been inadvertently passed, certified and paid for, forthwith rectify or remove and reconstruct the Work so specified and provide other proper and suitable materials or articles at his own cost. In the case of any such failure the Engineer-in-Charge/Project Manager may on expiry of notice period rectify or remove and re-execute the Work or remove and replaced with others, the materials or articles complained of to as the case may be at the risk and expense in all respects of the Contractor. The decision of the Engineer-in-Charge/Project Manager as to any question arising under this clause shall be final and conclusive. | Clause has been suitably amended to provide more clarity against documentary proofs
46 | Special Conditions of Contract (SCC) | 3 of 11 | 3.3.1 | Commissioning of all of the Plants in total along with Completion of Facilities in line with Technical/ Functional/ Performance Requirement stated under this Tender Document. | Commissioning of all of the Plants. | Time period of the project is till the commissioning of the Plants. Accordingly, the same has been corrected.
47 | Instruction to bidders (ITB) & Schedule of Rates (SOR) | REPLACE "CELL NO I 28" WITH "CELL NO K 28" WHILE READING THE RESPECTIVE CLAUSES |  |  | "CELL NO I 28" is replaced with "CELL NO K 28", wherever appearing in the entire tender document. "CELL NO I 28" should be read as "CELL NO K 28" at all the respective places of the tender document. | CELL Nos has been amended due to the incorporation of additional columns in the Revised SOR sheet
48 | Schedule of Rates | Revised Format for Schedule of Rates (SOR) has been added with changes in SOR-1. This revised SOR format will supersede the earlier SOR format & this revised SOR only will be used for filling up the Financial Bids. |  |  | 1) Schedule of Rates, SOR-1 has been amended with the addition of the provision for filling the applicable Safeguard duty (if applicable) in the form of % (Percentage) and amount. Bidders are required to fill the % and amount of the Safeguard duty in SOR-1, if applicable, else the same will be left blank/Zero. 2) Earlier Schedule of Rates uploaded at the time of tendering will not be considered for the Financial Bids evaluation purpose & only this revised Schedule of Rates, as attached with amended SOR-1 will be considered. Bidders are required to refer this revised SOR only. 3) Applicable Safeguard duty will be filled by the bidder in SOR-1 mentioning the % (Percentage) & amount in figures of the Safeguard duty. Both percentage & amount in figures for the Safeguard duty, if applicable, is mandatory to be filled in the SOR-1. 4) The amount of the Safeguard duty so mentioned in the SOR-1 by the bidder will form the part of Financial Bids evaluation & will be considered while calculating the total Evaluated Bid value. 5) Owner shall reimburse the amount of Safeguard duty (If applicable) mentioned in the Financial Bid (SOR-1) of the successful bidder, against the production of documentary Proofs only, with a maximum ceiling of safeguard duty amount, which is mentioned under the SOR-1. No Safeguard duty will be reimbursed to the successful bidder in the absence of documentary proofs. 6) In case of any reduction in the % (percentage) of the Safeguard duty in due course of the performance of the contract, the reimbursement of the safeguard duty will be done as per the revised percentage only against the production of documentary proofs. The Safeguard duty at the higher percentage (If applicable), mentioned under the SOR-1 initially during the bidding stage will not be applicable here & the reimbursement will be done as per the reduced percentage & thereby the reduced amount only. 7) In case of the waiver of the Safeguard duty in the due course of the performance of the contract, no reimbursement on account of Safeguard duty will be paid to the contractor. | Revised schedule of Rates has been made for the incorporation of Safeguard Duty
49 | Special Conditions of Contract (SCC) | 6 of 11 | 6.2 | During the demonstration of yearly CUF, any shortfall in generation below the committed annual CUF will be penalized @ INR 5.65/Unit. The CUF shall be evaluated as per the formula mentioned Section VII, Scope of Work and Technical Specifications. | Kindly refer Annexure-IV to Amendment-1.
50 | Special Conditions of Contract (SCC) | 5 of 11 | 6.1 | During the Operational Acceptance after providing 03 chances for the PR demonstration, any shortfall in the Performance Ratio (PR) as determined through the PR Test Procedure specified in Section VII, Scope of Work and Technical Specifications, & “PERFORMANCE GUARANTEE TEST PROCEDURE”, will attract imposition of penalty. For every 0.01 shortfall in PR below 0.78, a penalty of 1% of the total Contract Value (i.e., total sum of all the Supply , Service and absolute value of O & M Contract) shall be levied. In case the Contract Performance Security has already been encashed on account of any default/delays, the penalty amount will be recovered from any due payments to the contractor. In case the Plant PR result is less than 0.73, then the total plant will be rejected & the total Contract Performance Security submitted by the contractor will be forfeited & no further payments due to the contractor will be made. | During the Operational Acceptance after providing 03 chances for the PR demonstration, any shortfall in the Performance Ratio (PR) as determined through the PR Test Procedure specified in Section VII, Scope of Work and Technical Specifications, & “PERFORMANCE GUARANTEE TEST PROCEDURE”, will attract imposition of penalty. For every 0.01 shortfall in PR below 0.78, a penalty of 1% of the total Contract Value (i.e., total sum of all the Supply , Service and absolute value of O & M Contract) shall be levied. In case the Plant PR result is less than 0.73, then the total Contract Performance Security submitted by the contractor will be forfeited. In case the Contract Performance Security has already been encashed on account of any default/delays, the penalty amount will be recovered from any due payments to the contractor.
51 | Technical Specifications | 115 of 136 | 38.23 | Fasteners and washers to be used for erection of mounting structures and those for fixing Module over MMS shall be of stainless steel grade SS 304 & SS 316 with property class A-70 conforming to relevant ISO standard and must sustain the adverse climatic conditions to ensure the life of the structure for 25 years. | Fasteners and washers to be used for erection of mounting structures and those for fixing Module over MMS shall be of stainless steel grade SS 304 & SS 316 respectively with property class A-70 conforming to relevant ISO standard and must sustain the adverse climatic conditions to ensure the life of the structure for 25 years.

## Clarifications
NIT No: SECI/C&P/NIT/2018/SCCL150
Notice Inviting Tender For Design, Engineering, Supply, Construction, Erection, Testing & Commissioning of 129 MW (AC) Solar PV Power Plant under Domestic Competitive Bidding Singareni Collieries Company Limited (SCCL), Telangana
Sl. No. | Description as per Tender Document | Queries | Category | Clarifications
1 | ELIGIBILITY CONDITIONS SET FORTH IN THE TENDER DOCUMENT ARE AS PER 150 MW (AC) CUMULATIVE CAPACITY BASIS ONLY. BIDDERS ARE REQUIRED TO QUOTE ACCORDINGLY FOR THE COMPLETE CUMULATIVE CAPACITY OF 150 MW (AC). THE TOTAL CAPACITY OF 150 MW WILL BE AWARDED TO A SINGLE SUCCESSFUL BIDDERS ONLY SELECTED AFTER E-RA ON INDIVIDUAL SITE BASIS | We request you to kindly amend this clause as "THE TOTAL CAPACITY OF 150 MW WILL BE AWARDED TO A SINGLE SUCCESSFUL BIDDERS ONLY SELECTED AFTER E-RA. | Contractual | Bidders are required to refer Sr No 40, Amendment-1
2 | OWNER RESERVES THE OPTION TO REDUCE ANY OF THE ABOVE-MENTIONED SITE CAPACITY FROM THE OVERALL CUMULATIVE CAPACITY BEFORE/AFTER AWARD OF CONTRACT AGREEMENT. ACCORDINGLY, THE TOTAL PROJECT PRICE WILL BE PROPORTIONATELY REDUCED & THE FINAL PROJECT PRICE ARRIVED AS SUCH AFTER REDUCTION WILL BE THE FINAL PROJECT PRICE OF THE CONTRACT AGREEMENT. | We request you to kindly delete this clause as the per MW price arrived by you is based on the cumulative capacity of 150 MW and will not be applicable/workable on reduced capacity. | Contractual | Terms & conditions of the original Tender document will prevail
3 | Second Contract (O&M Part): For providing Comprehensive operation & maintenance of the Solar PV plant for 10 (Ten) years from the date of commissioning or Operational Acceptance, whichever is later, as detailed in technical specification including supply and storage of all spare parts, consumables, repairs/ replacement of any defective equipment etc. | As we will provide the training to your personnel, it will be cost effective to keep the O&M in your scope after 3 years. Hence we request you to kindly reduce the O&M period of the contract to 3 years, which will enable us to quote our competitive price. | Contractual | Terms & conditions of the original Tender document will prevail
4 | However, the above-mentioned contract award methodology may be modified/ changed based on specific project requirements and upon sole discretion of Owner. | As per our understanding, owner may decide single / two contracts for the individual /cumulative capacity of the sites. Please confirm that Owner will not increase/decrease the tendered capacity of 150 MW Project. | Contractual | Terms & conditions of the original Tender document will prevail
5 | Land for Residential Accommodation : No Land shall be made available for residential accommodation for staff and labour of Contractor. | As the sites are at remote places, we request you to permit to have godown & labour colony within the proposed site for having execution advantage. We will dismantle all the labour colonies and will use 100% of the proposed site for the SPV Plant. | Contractual | Terms & conditions of the original Tender document will prevail
6 | However, where value of BG is Rs.5 lakhs and above, the BG should be obtained from the bank branches situated at Hyderabad / Kothagudem or operative and payable at bank branches situated at Hyderabad/ Kothagudem | We request you to kindly delete this clause, as some of the banks proposed by you in the tender document are not accepting this clause. | Contractual | Terms & conditions of the original Tender document will prevail. Bidders are required to refer Clause 5 of SCC.
7 | If, after the date seven (7) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the Performance of any of its obligations under the Contract. However, these adjustments would be restricted to direct transactions between the Owner and the Contractor. This adjustment shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor and shall also not be applicable on bought out items dispatched directly from sub- vendor works to site. | We request you to kindly amend this clause as followed by NTPC and other PSU's. If, after the date seven (7) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. However, these adjustments would be restricted to items in respect of direct transactions between the Employer and the Contractor and Bought out items (to be dispatched directly from the sub-vendors' works to Employer’s site). | Contractual | Terms & conditions of the original Tender document will prevail
8 |  | As per the Government Notification No. 1/2018-Customs (SG) dated 30.07.2018, safeguard duty is applicable on imported SPV modules and as on date the same is to be included in the quoted Price. We request your confirmation on the same. | Contractual | Bidders are required to exercise their appropriate Due Diligence while submitting their respective Bid Prices. Bidders are required to refer the Sr No 48, Amendment 1 in regard of the Safeguard duty.
9 | Bidder should quote all-inclusive prices including the liability of GST (in line with the given SOR Format) whether on the works contract as a whole or in respect of bought out components used by the Contractor in execution of the Contract. Owner/Employer shall not be responsible for any such liability of the Contractor in respect of this Contract | We request you to kindly amend the price schedule as excluding GST which shall be payable by you extra at actuals. This will help us in submitting competitive offer. This will also help in accounting the statutory variations to the contract Price. | Contractual | Terms & conditions of the original Tender document will prevail
10 | (2) Annual Generation Guarantee up to a period of 10 years (O&M Period), starting from the date of Operational Acceptance. | We would like to inform you that the annual generation requirement is not mentioned in the tender. Request you to kindly provide your requirements. | Technical | Kindly refer S.No.6 Amendment-1.
11 | It is the responsibility of the Contractor to build-in the expected variation of irradiance in their design by installing additional DC capacity to meet the committed CUF. Irradiance variation will not be considered for the calculation of CUF. | We would like to inform you that the generation depends on external parameters such as actual radiation, atmospheric temperature, grid availability, and force majeure situations which are beyond prediction. So we request uou to kindly allow the correction of generation with respect to the external parameters and revise the clause accordingly, as followed by other PSUs. | Technical | Terms & conditions of the original Tender document will prevail.
12 | Electrical Interconnection : Substation details | We understand the connectivity approval to the TRANSCO will be taken care by SCCL. We request your confirmation in this regard. | Technical | Approval for connectivity to the designated substation will be taken by SCCL. However, all approvals which will be required for interconnection, evacuation, bay construction, commissioning, etc shall be taken by the Contractor.
13 | Electrical Interconnection : Substation details | For all the five sites, we request you to kindly confirm the receiving station details with SLD and Layout to enable us to estimate Transmission line length and the receiving end bay construction requirements. | Technical | Details of substation are provided in the tender. Bidder may visit the site and the respective substation for SLD, Layout and transmission line routing details.
14 | Electrical Interconnection : Substation details | We request you to confirm whether the constructed plants are grid connected or for captive usage. If it is grid connected, kindly confirm whether Open access agreements are signed between you and TRANSCO for these proposed plants. | Technical | The plants are intended for captive usage but open access will be required for consumption of the generated energy at different SCCL locations. SCCL shall make the application for Open Access. However, the Contractor shall facilitate SCCL in obtaining the same.
15 | Site preparation activities | As discussed in the pre-bid meeting, we found number of trees, encroachments, graves, nallas, roads, HDPE pipes & LT/HT line crossings in the proposed sites. Hence we request you to kindly include tree cutting, removal of encroachments, diversion of nallas, roads and Line crossing in your scope so as to enable the contractor to complete the work within the completion period. | Technical | Uprooting of eucalyptus trees and diversion of existing nalla, pipeline and transmission line will be done by SCCL. Site preparation including cutting of trees (other than eucalyptus), levelling and grading are in the scope of the Contractor.
16 | Site Layouts | We request you to provide the proposed site layout in Auto cad format to facilitate our design working. | Technical | Attached. However, it shall be noted that the given site layouts are indicative only.
17 | The peripheral wall will be constructed by SCCL and hence can be taken out from the scope of the contractor. | We presume that there is no need of chainlink fencing/boundary wall around the sites (Package 1 to 5) is to be considered in our scope. Please confirm. | Technical | SCCL will construct boundary wall with Chainlink fence and Gate at all sites.
18 | Electrical Interconnection : Substation details : 132/33 kV SCCL S/s. | We presume that the power generated will get connected at 132 kV Bus of TRANSCO Side not to the SCCL side. If the connection is to the TRANSCO side, existing boundary wall needs to be dismantled and new boundary wall to be constructed, hence request you to confirm the scope. | Technical | For open access arrangement to take place, the power generated will be required to be fed into the TSTRANSCO side. However, all approvals for setting up bay and interconnection to be taken up by the Contractor.
19 | Electrical Interconnection : Substation details : 33/3.3kV SCCL Auxiliary S/s. | In the Pre-bid it is confirmed that the connectivity is at 11 kV level, whereas it is mentioned in the tender document as 33/3.3kV. Request you to kindly amend the connectivity voltage and provide the method of connection to the existing system. | Technical | Kindly refer S.No.6 of Amendment-1.
20 | Cell type : Multi-crystalline | We request you to kindly amend the cell type as "Mono Crystalline/Multi-crystalline so as to enable us to offer you competitive price. | Technical | Kindly refer S.No.14 of Amendment-1.
21 | Rated power at STC : 330 Wp or more | We request you to kindly amend it as 320 Wp or above so as to offer you a better price. | Technical | Kindly refer S.No.14 of Amendment-1.
22 | The glass used to make PV Modules shall be toughened low iron glass with minimum thickness of 4.0 mm. | We request you to amend this clause as follows: The glass used to make PV Modules shall be toughened low iron glass with minimum thickness of 3.2 mm. | Technical | Kindly refer S.No.15 of Amendment-1.
23 | Water vapour transmission rate < 2 g/m2/day | We request you to amend this clause as follows: Water vapour transmission rate ≤ 2 g/m2/day | Technical | Terms & conditions of the original Tender document will prevail
24 | Elongation at break > 100% | We presume that the mentioned values are for Machine Direction(MD) and will not be applicable for transverse direction (TD). Kindly confirm. | Technical | Mentioned values are for both TD and MD.
25 | The Employer reserves the right to conduct Pressure Cooker (PC) test/ Highly Accelerated Stress Test (HAST) to confirm the durability of the back sheet in accelerated conditions. | We request you to kindly confirm whether this test is to be conducted during execution. Deletion of this clause helps in meeting the completion time as well as cost reduction. Hence request you to delete this clause. | Technical | The test may be conducted before dispatch. Terms & conditions of the original Tender document will prevail
26 | Every SMU input shall be provided with fuses on both positive and negative side. | As per the standard practice, fuses will be provided either of positive or negative side and not on both the sides. Hence we request you to kindly amend this clause as "Every SMU input shall be provided with fuses on either positive or negative side" | Technical | Terms & conditions of the original Tender document will prevail
27 | The average voltage drop in the cables (Modules to Inverter) shall be limited to 1.5 % of the rated voltage. | We request you to kindly amend this clause as follows: The average voltage drop in the cables (Modules to Inverter) shall be limited to 2% of the rated voltage | Technical | Terms & conditions of the original Tender document will prevail
28 | Auxiliary Transformer : Voltage Ratio - 33 kV/0.415 kV Service & Application - Continuous application (Outdoor/Indoor) | Instead of centralized auxiliary distribution from delivery station, proposing distributive type auxiliary distribution taking tap off, from LV side of inverter duty transformer at respective inverter room / control room. Kindly confirm. | Technical | As per Clause 5.2 of Technical Specifications, voltage ratio of auxiliary transformer can be as per system design. No specific ratio is mentioned.
29 | The numerical relay shall have RS-232/RS-485/RJ-45/USB ports on front side for local communication with PC and on rear side for remote communication to SCADA system. | Bidder wants to clarify that, Numerical relay time synchronization with SCADA shall be subject to approved vendors and the product availability. The same shall be considered during detailed engineering. Kindly confirm | Technical | The numerical relay shall have RS-232/RS-485/RJ-45/USB ports for remote communication to SCADA system. Proposed makes with such provision shall be considered during detailed engineering.
30 | Following consideration shall be taken into account while sizing the auxiliary transformer: (i) 20% future load margin (ii) 20% design margin (iii) Total connected load at 0.8 power factor | Instead of taking cumulative margin of 40% ( 20% for load margin and 20% design margin ) shall consider only for 20% design margin for auxiliary transformer(s). Kindly confirm. | Technical | Terms & conditions of the original Tender document will prevail
31 | Accessories :4. Intelligent UPS (on line): Minimum 2 hour battery backup | Bidder suggests that, as SCADA is already powered with UPS with required backup duration, Intelligent UPS for each Workstation shall not be required standardly. Kindly confirm. | Technical | Separate Intelligent UPS for each Workstation is not required. The UPS for SCADA as required under Clause 10.2.1 shall be sufficient to supply backup power for 2 hours.
32 | 21.2 Temperature Sensor: The temperature sensor shall be Resistance Temperature Detector (RTD)/ Semiconductor type with measurement range of 0°C to 80°C. 21.3 Anemometer: a. Velocity Range: 0-60m/s with +/-2% accuracy @12 m/s; Resolution: 0.01m/s b. Wind direction: to 360 deg (No dead band) with +/-2 deg. accuracy @12 m/s; c. Resolution: 1 deg. d. Output: RS232 and RS485 | Temperature Sensor: Bidder suggests that, to attain good accuracy in temperature measurement, based on market availability of sensors, the Temperature Sensors for Solar application shall have measuring range till 70 deg. C (instead of 80 deg. C). Kindly confirm. Anemometer: Bidder suggests that, Wind speed and direction sensor (Ultrasonic type, Accuracy, output protocol and etc.) specifications shall be checked as per market availability and approved vendor list, during detailed engineering. Based on that, standard Anemometers shall be considered. kindly confirm. | Contractual | Terms & conditions of the original Tender document will prevail
33 | 21.4.1 Data logger and Data Acquisition System: (v). Connectivity and Data transmission: * Built-in GSM/ GPRS modem for wireless data transmission to SCADA / cloud server (procurement of GPRS enabled SIM Card and connection subscription to be the responsibility of Contractor). * RS485 MODBUS interface for data collection and storage on SCADA * Web interface with provision for user login to enable viewing and downloading of weather data in XLS/ CSV format (ix) Protection level: IP65 | (v). Connectivity and Data transmission: * Bidder suggests that, Weather station communication to SCADA shall be Wired (RS 485) or Wireless (GSM/GPRS) - subject to approved Vendor recommendation and as per site conditions. The same shall be decided by bidder during detailed engineering. kindly confirm. * For Web interface, bidder suggests that, subject to Vendors, the data download from Datalogger shall be decided (whether it is a application software or web interface). kindly confirm. (ix) Protection level: IP65 Bidder wants to clarify that, Dataloggers are not IP 65 type. however, it is placed inside a enclosure, that shall be IP 65 type. kindly note & confirm. | Technical | 1. Weather station communication to SCADA may be wired or wireless and the same may be decided during detailed engineering. 2. Data download from Datalogger may be through application software or web interface. 3. Datalogger Enclosure shall be IP65
34 | 22.1 CCTV Camera i) Main entry: Covering all the entry/exit 24 hours (ii) Along the Plant Perimeter: Covering complete perimeter of Plant Area to capture all possible intrusion (iii) Control Rooms: Covering Entry/Exit and activities within Control Rooms (iv) The Contractor has to propose the locations and number of cameras required for the Plant during bidding, however Employer’s decision on number of cameras shall be final. 22.5 It shall be possible to control all cameras i.e., PTZ auto/ manual focus, selection of pre-sets, video tour selection etc. | 22.1.(iv) Bidder requests for max. limit of Camera quantities (if any) for considering in the Design. 22.5 Bidder suggests that, the camera type (PTZ / Fixed) shall be decided by Bidder based on location and its purpose, during detailed engineering. Kindly confirm. | Technical | Kindly refer S.No.18 of Amendment-1.
35 | Data acquisition system with remote monitoring facilities: As per SLDC’s Requirement data shall be sent from generating plant to the State Load Dispatch Centre (SLDC) | Bidder informs that, Data transfer from SCADA to SLDC shall be as per Statutory guidelines and SLDC standards. The same shall be considered during detailed engineering. Kindly confirm on any SLDC requirements (if known) | Technical | Determination of SLDC requirements for transfer of data shall be in the scope of the Contractor.
36 | The lighting system for outdoor and indoor areas of solar power plant shall be designed in such a way that uniform illumination is achieved. Average LUX level to be maintained in different areas shall be as under: Other areas including periphery wall 10 Lux | Kindly clarify street light shall be provided only for peripheral road and not for internal roads. | Technical | As per Clause 20.3.2 of Technical Specifications, average lux level required for peripheral and internal roads is 4 lux.
37 | In case the contractor proposes to provide concrete pile; the type, dia. and length of pile shall be as per recommendations of Geotechnical investigation report corresponding to prevalent soil characteristics at site. However, the min. dia. and depth of the pile shall be 300mm and 1800mm respectively | Diameter and depth of pile shall be based on soil report and loads acting on the foundation. Kindly confirm. | Technical | Terms & conditions of the original Tender document will prevail
38 | Fasteners and washers to be used for erection of mounting structures and those for fixing Module over MMS shall be of stainless steel grade SS 304 & SS 316 | We propose to use S304 bolts for fixing of modules. Kindly confirm | Technical | Terms & conditions of the original Tender document will prevail
39 | Fasteners and washers to be used for erection of mounting structures and those for fixing Module over MMS shall be of stainless steel grade SS 304 & SS 316 with property class A-70 conforming to relevant ISO standard and must sustain the adverse climatic conditions to ensure the life of the structure for 25 years | Fasteners and washers to be used for erection of mounting structures shall be GI bolt of 5.6 grade as per IS 1367 (part-3). However for module fixing we shall use SS 304 B&N. Kindly confirm. | Technical | Terms & conditions of the original Tender document will prevail
40 | Unless otherwise specified elsewhere, all buildings except Security room/ cabin shall have RCC framed structure. | We suggest Inverter room shall be of prefab type. Kindly confirm. | Technical | Terms & conditions of the original Tender document will prevail
41 | The water proofing treatment shall be in situ five course water proofing treatment with APP (Atactic Polypropylene) modified Polymeric membrane over roof consisting of first coat of bitumen primer @ 0.40Kg per sqm, 2nd & 4th courses of bonding material @ 1.20 kg/sqm, which shall consist of blown type bitumen of grade 85/25 conforming to IS : 702, 3rd layer of roofing membrane APP modified Polymeric membrane 2.0 mm thick of 3.00 Kg/sqm weight consisting of five layers prefabricated with center core as 100 micron HMHDPE film sandwiched on both sides with polymeric mix and the polymeric mix is protected on both sides with 20 micron HMHDPE film | Water proofing shall be as per NBC sode as mentioned below: a. Apply a cement slurry coat using 2.75Kg/Sq.m of Cement admixed with ( Sika Latex or equivalent) water proofing compound. b. Apply 20mm thick layer of cement mortar of mix 1:5 admixed with (Sika Latex or equivalent) water proofing compound to required slope. c. Lay 100 mm thick bricks with 10mm to 15mm gap between the bricks and gaps filled with cement mortar (1:5) admixed with (sika Latex or equivalent) water proofing compound and compact it. d. After proper curing, apply 2nd coat of cement slurry admixed with water proofing compound. e. prepare the top surface with 20mm thick joint less cement mortar mix (1:4) admixed with water proofing compound & finished the surface with cement slurryby using trowel. Kindly confirm | Technical | Terms & conditions of the original Tender document will prevail
42 | Award of Contract ...Both contracts will contain a cross fall breach clause specifying that breach of one will constitute breach of the other.. | Cross fall breach clause in both contracts may lead to classification of both contracts as works contract attracting GST @ 18% and project may not be able to avail GST @ 5% available for SPGS (Solar Power Generation System). We request to remove this clause and address the concern regarding breach in one contract through some other means. | Contractual | Terms & conditions of the original Tender document will prevail
43 | Power of Attorney for authorized signatory in non-judicial stamp paper (as per ‘Form F-24’) | Ca we submit our standard Power of Attorney for authorized signatory as it is difficult to obtain POA for every tender? The same is being accepted by all PSUs. | Contractual | General Power of Attorney (GPA) can be accepted in exceptional cases subject to Board Resolution & production of certified copy of the GPA
44 | MSEs ...shall be exempted from Tender Processing Fees and EMD submission | The exemption to MSEs from EMD submission may lead to adventurous bids by MSEs which may not be feasible considering technical complexities of the Project. Please ensure that any bidder under pretext of this clause may not lead to unrealistic bid price as there is elimination of top 50% bids from e-RA. | Contractual | Bid Processing Fee has been revised to Rs 25000/- (INR Twenty Five Thousand only). Bidders are required to refer the Sr No 41, Amendment I for the same.
45 | The Bid Processing Fees and EMD are exempted for MSME Vendors/ Developers registered under NSIC/ DIC/ Udyog Aadhaar Category only. | The exemption to MSEs from EMD submission may lead to adventurous bids by MSEs which may not be feasible considering technical complexities of the Project. Please ensure that any bidder under pretext of this clause may not lead to unrealistic bid price as there is elimination of top 50% bids from e-RA. | Contractual | Bid Processing Fee has been revised to Rs 25000/- (INR Twenty Five Thousand only). Bidders are required to refer the Sr No 41, Amendment I for the same.
46 | Tender processing fee: INR 46,90,500/- (Indian Rupees Forty Six Lacs & Ninety thousand and Five hundred only) inclusive of GST @ 18% | Request you to reasonably take the tender processing between Rs.5000 to Rs. 10000/- only | Contractual | Bid Processing Fee has been revised to Rs 25000/- (INR Twenty Five Thousand only). Bidders are required to refer the Sr No 41, Amendment I for the same.
47 | For every 0.01 shortfall in PR below 0.78, a penalty of 1% of the total Contract Value (i.e., total sum of all the Supply , Service and absolute value of O & M Contract) shall be levied. In case the Contract Performance Security has already been encashed on account of any default/delays, the penalty amount will be recovered from any due payments to the contractor. In case the Plant PR result is less than 0.73, then the total plant will be rejected & the total Contract performance Security submitted by the contractor will be forfeited & no further payments due to the contractor will be made. | Please restrict the penalty to 5% of EPC Contract value only as PR shortfall does not reflect O&M deficiency. | Contractual | Terms & conditions of the original Tender document will prevail
48 | Interest bearing adjustable initial advance (OPTIONAL) of 10% of the Contract Value (i.e., total sum of all the Supply Contract) shall be released to successful bidder upon receipt of unconditional acceptance of NOA | Interest bearing advance may kindly be amended as non-interest bearing advance as the present clause will lead to huge working capital cost and increase the bid price consequently. Also no sub-vendor such as Module/PCU/etc OEMs work without advance. | Contractual | Terms & conditions of the original Tender document will prevail
49 | Twenty percent (20%) payments shall be paid against successful erection, testing and commissioning of materials at site and Operational Acceptance of the Facility pursuant to successful Guarantee Tests and demonstration of Performance Ratio (PR) including submission of all as-built drawings and documents. | Please do not link supply payments with services contract activities as it will lead to classification of supply contract also as works contract leading to higher tax implications. Please release 90% supply payments on receipt at site and 10% on successful operational acceptance/ PR Test. | Contractual | Terms & conditions of the original Tender document will prevail
50 | Final Ten percent (10%) payment of Supplies shall be paid after CUF demonstration on completion of first year of O&M of the Facility pursuant to submission of all requisite documentation | Please release the final payment on completion of PR Test as there is no need to hold 10% of contract value for such a long period of 1 year as contractor will submit BG of 10% of EPC + O&M Price, so your concerns against poor performance are safeguarded by PBG. The present clause is unnecessarily leading to cash flow problems to EPC Contractor and consequently bid prices may be higher. Similar change is requested for Services contract as well. | Contractual | Terms & conditions of the original Tender document will prevail
51 | It is the responsibility of the Contractor to build-in the expected variation of irradiance in their design by installing additional DC capacity to meet the committed CUF. Irradiance variation will not be considered for the calculation of CUF. | This clause is highly unreasonable, as EPC Contractor cannot be expected to control solar irradiance. Even if the installed capacity is increased, EPC Contractor cannot be expected to achieve CUF if solar irradiance is very poor in certain period. A developer is expected to take solar irradiance risk in its own scope as low CUF due to poor irradiance does not indicate quality of EPC work or system supplied and so all project risks need not be passed on to EPC contractor. Please provide adjustment due to Irradiance variation as otherwise most of reputed EPC Players consider such blanket risks and uncontrollable liabilities as strict NO-GO for tenders with such kind of clauses. No other PSU (e.g. NTPC, NHPC, GIPCL, APGENCO,etc) keep such absolute generation guarantee clause in their tender. | Technical | Terms & conditions of the original Tender document will prevail.
52 | In case the Project fails to generate any power continuously for 1 month any time during the O&M period, apart from the force majeure and grid outages as certified by competent authority, it shall be considered as “an event of default”. In the case of default, the entire Contract Performance Security will be forfeited & the Owner may terminate the O&M contract. | If the plant does not generate power due to very poor solar irradiance or bad weather conditions such as rainfall, etc., the same may kindly covered under force majeure. Please confirm. | Technical | Terms & conditions of the original Tender document will prevail
53 | The glass used to make PV Modules shall be toughened low iron glass with minimum thickness of 4.0 mm. The glass shall have transmittance of above 90%. | Please asllow 3.2 mm for 72 cell module as well as same in being accepted widely. | Technical | Kindly refer S.No. 15 of Amendment-1.
54 | The contractor shall design and install the effective module cleaning system. | Please confirm the source of water supply and water quality test reports, if available. | Technical | The same shall be arranged by the Contractor at its cost.
55 | During the demonstration of yearly CUF, any shortfall in generation below the committed annual CUF will be penalized @ INR 5.65/Unit. | As the sites are surrounded by coal dumping yard and there is very dust at different times of day and because of this the generation will be affected. Under such scenarios, we suggest to mutually finalize the guarantee generation figures only during detailed engineering. Also, the penalty of Rs 5.65 is way too high. Request you reduce the same. | Technical | Terms & conditions of the original Tender document will prevail
56 | During the demonstration of yearly CUF, any shortfall in generation below the committed annual CUF will be penalized @ INR 5.65/Unit. | Please provide Reference Irradiance Data such as Meteonorm, NASA, etc. so that we can estimate generation. In absence of Reference Irradiance Data we may not be able to work out generation. Please provide basis of requisite PR of 78% and CUF. | Technical | The Bidder shall consider suitable radiation database for estimation of generation during bid preparation.
57 | General construction | Please confirm the requisite tree removals & grading and levelling work at site shall be done by the Client and the time when suitably graded site shall be handed over to Contractor for execution activities. | Technical | Uprooting of eucalyptus trees and diversion of existing nalla, pipeline and transmission line will be done by SCCL whereas Site preparation including cutting of trees (other than eucalyptus) and grading and levelling is in the scope of the bidder.
58 | Statutory Approvals | Open Access approval application may be submitted and all follow-up activities can be taken up by contractor. But, if open access approval is denied by authorities or delayed, then contractor cannot be held responsible as it is beyond contractor's control. | Technical | Terms & conditions of the original Tender document will prevail.
59 | Site location single coordinate has mentioned in tender | Proper Boundary Coordinates are required for all the 5 sites along with the autocad drawings. | Technical | Attached. However, it shall be noted that the given site layouts are indicative only.
60 | Labor Laws | What type of labour compliance is require, If there is any special condition or requirement, please mention the same. | Contractual | Terms & conditions of the original Tender document will prevail
61 | Area Grading and Land Development | Area grading and land development work - Is Grading in contractor scope as mentioned in in technical specification? | Technical | Yes.
62 | Roads | Road specification is 20 mm thick pre-mix carpet. Is this 20 mm thick Concrete or Bitumen on top of road. | Technical | Kindly refer S.No.19 of Amendment-1.
63 | Bidders are required to ascertain the correctness of amount related to Goods & Service Tax (GST) as mentioned in the SOR/ PS as on the date of techno-commercial bid opening as | GST or Tax rate may be considered differently by various participants so please clarify the financial bid evaluation criteria. Whether it will be evaluated on basic price (excluding GST) or overall price? | Contractual | The Price bid evaluation will be done on all inclusive price inclusive of GST.
64 | Work Completion Schedule | Considering site conditions, it will be very difficult to execute the Project within 9 months. Request you to please consider 14 month from LOA. | Contractual | Terms & conditions of the original Tender document will prevail
65 | At the option of the Employer/ Owner, the work for which the Tender had been invited, may be awarded to one Contractor or split between more than one bidders, in which case the award will be made for only that part of the work, in respect of which the bid has been accepted. The quoted rates should hold good for such eventualities. | It will be difficult for the bidder to go for reverse auction as bidder is bidding for 150 MW and then the owners will convert it into per MW price. If small package will be given to the contractor and other blocks are given to another contractor or other blocks are not awarded then there is financial loss to the bidder. request you either delete the clause or amend it to One bidder will get 150 MW (no partial award). | Contractual | Bidders are required to refer Sr No 40, Amendment-1 for the same.
66 | Cell type - Multi-crystalline Rated power at STC - 330 Wp or more No negative tolerance is allowed | We request SCCL to amend the clause as follows: Cell type - Multi-crystalline Rated power at STC - 310 Wp or more No negative tolerance is allowed. Kindly accept. | Technical | Kindly refer S.No.14 of Amendment-1.
67 | 50 MW Ramagundam Site Queries | During the site visit, few graves have been observed inside the land marked for the solar plant. Kindly inform what is needed to be done. | Technical | Graveyard will be isolated and compensatory land will be provided near site.
68 | 50 MW Ramagundam Site Queries | We understand that the 400 V line passing through the site needs to be removed. We request SCCL to arrange for the same. | Technical | SCCL will re-route the existing LT Lines in the Plant Area.
69 | 50 MW Ramagundam Site Queries | We understand that the village road passing through the site needs to be reshifted and we request SCCL to kindly arrange the same. | Technical | SCCL will provide equivalent land near site.
70 | 50 MW Ramagundam Site Queries | We request SCCL to clarify the evacuation point for the power generated from the solar plant. | Technical | Kindly refer Clause No. 1.1 of Scope of Works for interconnection details.
71 | 50 MW Ramagundam Site Queries | We request SCCL to arrange for the jungle clearance permission from the authorities. | Technical | Contractor to arrange for the same.
72 | 50 MW Ramagundam Site Queries | We understand that the water pipeline passing through the site needs to be shifted and the same shall be in scope of SCCL. | Technical | There is no water pipeline in the allocated area / site.
73 | General | Please share ACAD drawing in order to give a valid commitment of energy generation with respect to actual shadow free area available. | Technical | Attached. However, it shall be noted that the given site layouts are indicative only.
74 | SLD | As per the referred clause, Spec. referring SLD and the same is not available in tender documents. Customer may please provide SLD( single line diagram). | Technical | SLD not applicable for the referred clause.
75 | DC Battery & Charger | We propose to derive the DC power from UPS system itself in Inverter rooms. Separate DC system is not envisaged in Inverter rooms. However separate DC system shall be provided in Main control room. Please review and confirm. | Technical | OK. Confirmed.
76 | Soil resistivity | Please provide the soil resistivity to be considered by bidder for tender estimate purpose. | Technical | SCCL is not having the soil resistivity details. As per Tender documents, contractor has to make arrangements for the same.
77 | Earth pits for SMB | Earth pits for SMB structures are not required. As all SMB structures shall be connected to the buried GI steps which shall be capable to meet the earthing requirements. Also it is standard practice of earthing DC system in a solar plant, which has been followed in our earlier executed projects. However earth pits for Equipments in IR rooms and CMCS room (such as transformers, PCUs, Panels etc.) shall be provided as required for the system. Kindly confirm. | Technical | Kindly refer S.No.16 of Amendment-1.
78 | Number of cameras. | As per the referred clause, Number of cameras will be finalized by customer during execution of the project. However, Bidders proposal is that , in case during execution, customer requirement exceeds the bidders estimated BOQ then in such case unit rate shall be applicable. kindly confirm. | Technical | Kindly refer S.No.18 of Amendment-1.
79 | Dewatering pumps | As per the referred clause, Dewatering sumps are there in the project. Customer may please confirm Dewatering pumps are required or not. | Technical | As required during construction and O&M. Kindly refer S.No.44 of Amendment-1.
80 | Installation of Bore Well with Pump | Please furnish the level of underground ground water from NGL for installation of Bore Well. Please furnish scheme or P&Ids. Further, taking permission of digging borewell in the SPV area shall lies with owner. Kindly confirm. | Technical | Contractor to arrange for the same.
81 | Nearest 33kv substation | As per the referred clause, Location of 33kv substation at Yellandu is not clear and hence customer may please provide approximate distance from 10MW Block. | Technical | Kindly refer S.No.6 of Amendment-1.
82 | Type test charges | Valid type test certificates (less than 10 years old) shall be submitted during detailed engineering stage. Type test shall be conducted only if valid type test certificates are not available. Type test charges are not accounted at this stage, same shall be charged to customer during execution time if type test shall be required for any supplied equipment. This is inline with the type test requirements of Equipments indicated in bid specification. Customer may please confirm. | Technical | Type test charges, if any, shall be accounted before bidding itself. The Employer will not pay any type test charges.
83 | Topography Report & Contour map | Please furnish the topographical survey and contour map of the area to estimate the site levelling works and natural slope for drain works. | Technical | Contour map is shown in site layout. However, it shall be noted that the given contour mapt is indicative only and the Employer is not responsible for the accuracy of the map. It shall be the responsibility of the Contractor to plot contour map for detailed design.
84 | Soil Investigation report | Please furnish Soil Investigation report. | Technical | SCCL is not having the soil investigation report. Terms & conditions of the original Tender document will prevail.
85 | The ROW for the TL/UG cable shall be obtained prior to the construction of the line from the concerned authorities | Please clarify scope. Is there any private land through which the evacuation line has to be constructed? | Technical | Bidder may visit site for due diligence, however ROW is in the scope of bidder only.
86 | Scope of supply and work at NPDCL, SCCL, Manuguru substations | Please elaborate. | Technical | All supply and works required for evacuation of power along with the approvals, is in the scope of contractor. Terms & conditions of the original Tender document will prevail.
87 | The minimum thickness excluding anti corrosive treatment (BMT) of various elements of MMS structure shall be as following: • Stub/ column – 3.15mm, Rafter – 2.5mm & • Purlin & other members – 2.0mm | The thickness of MMS members to be arrived as per design calculations. Suggested thickness-( Column -2.5mm,Rafter -2.0mm and Purlin-1.6mm) | Technical | Terms & conditions of the original Tender document will prevail
88 | Fasteners and washers to be used for erection of mounting structures and those for fixing Module over MMS shall be of stainless steel grade SS 304 & SS 316 with property class A-70 conforming to relevant ISO standard and must sustain the adverse climatic conditions to ensure the life of the structure for 25 years. | Please specify the grade of stainless steel fasteners for Mounting Structure has to be SS304 and for PV Module fastening has to be SS316. For the above case grade of SS304 has to be A2 and SS316 has to be A4 . Please confirm. | Technical | Kindly refer S.No.51 of Amendment-1.
89 | Modules shall be clamped & bolted with the structure properly. The material of clamps shall be Al / SS – 316 having weather resistant properties. Clamp/bolt shall use EPDM rubber and shall be designed in such a way so as not to cast any shadow on the active part of a module. | Please specify if the PV-Modules have to be Clamped and Bolted both to the structure?? Also use of EPDM may be waived off as it may not last for 25 years in outdoor condition. | Technical | Kindly refer S.No.20 of Amendment-1.
90 | The length of one unit (Table) of MMS shall not generally be more than 20m. | Please review. | Technical | Terms & conditions of the original Tender document will prevail
91 | General | We request SCCL to allow the bidder to quote without GST and GST shall be paid at actuals so that all bidders are at same platform | Contractual | Terms & conditions of the original Tender document will prevail
92 | Amount: INR 46,90,500/- (Indian Rupees Forty Six Lacs & Ninety thousand and Five hundred only) inclusive of GST @ 18%. | BHEL being a CPSU, would request SCCL to waive off the tender processing fee or otherwise, at least, it could be according to the current market trends. Kindly Confirm. | Contractual | Bid Processing Fee has been revised to Rs 25000/- (INR Twenty Five Thousand only). Bidders are required to refer the Sr No 41, Amendment I for the same.
93 | If, after the date seven (7) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the Performance of any of its obligations under the Contract | We request SCCL to amend the clause as follows: If, after the date seven (7) days prior to the date of Bid Opening, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the Performance of any of its obligations under the Contract. Kindly Accept. | Contractual | Terms & conditions of the original Tender document will prevail
94 | General | We request that Anti Dumping Duty, Safeguard Duty shall be borne by SCCL. Kindly Accept. | Contractual | Terms & conditions of the original Tender document will prevail
95 | General | If delay from scheduled completion is on account of employer, then any statutory variation beyond stipulated Delivery/ Commissioning/Completion schedule shall be to customer’s account. | Contractual | Terms & conditions of the original Tender document will prevail
96 | General | Applicable taxes & duties on contract cancellation charges shall be on account of employer. | Contractual | Terms & conditions of the original Tender document will prevail
97 | Payment terms: Interest bearing adjustable initial advance (OPTIONAL) of 10% of the Contract Value (i.e., total sum of all the Supply Contract) shall be released to successful bidder upon receipt of unconditional acceptance of NOA…………………………..MCLR + 3.5% as applicable. Successful bidder will be required to submit the individual ABGs on individual site basis for claiming the advance amount. | We request to give interest free advance. Kindly accept. We request to submit unconditional Bank Guarantee for 100% of advance amount. Kindly accept. | Contractual | Terms & conditions of the original Tender document will prevail
98 | In consideration of the Singareni Collieries………………..Branch, Hyderabad / Kothagudem. | We request SCCL to remove the assignee clause from CPBG. Kindly Accept. | Contractual | Terms & conditions of the original Tender document will prevail
99 | The glass used to make PV Modules shall be toughened low iron glass with minimum thickness of 4.0 mm. | The proposed modules are already complying with IEC standards as required in the tender. Incorporating the additional requirement of thickness of 4.0 mm for 72 cell will make the project cost higher, further, such requirement of thickness is a non standard requirements. Hence, We request WBREDA to accept thickness of 3.2 mm also for 72 as a standard practice followed by SECI-THDCIL, WBSEDCL, WBPDCL, NTPC , Etc | Technical | Kindly refer S.No.15 of Amendment-1.
100 | 4 nos of pyronometer and 6 nos of temperature sensor | Pls confirm is these are required on per site basis or for total 150 MW Project. | Technical | The specified number of sensors shall be provided for every site.
101 | The Finished Grade Level (FGL) of the proposed plant shall be fixed with reference to the highest flood level (HFL) | We request SECl/SCCL to support us by providing HFL details. | Technical | The details were available in the attached site layouts.
102 | All statutory approvals/permissions and/or No Objection Certificates (NoC) etc. from the DISCOM for obtaining connectivity at the substation as per Project Particulars provided above. 32.1.4 In the matter of connectivity of Plant to DISCOM’s substation, the Owner will take the necessary connectivity permission. | The is contradiction in two clauses, we infer that SCCL will take grid connectivity permission.pls confirm. | Technical | Approval for connectivity to the designated substation will be taken by SCCL. However, all approvals which will be required for interconnection, evacuation, bay construction, commissioning, etc shall be taken by the Contractor.
103 | Any consecutive 30 days period (excluding interruptions that last entire day on account of grid outage or as per hindrance record maintained at site only) | Number of hours is not clarified, we infer that number of hours for grid outage should be excluded for PR Calculation | Technical | Kindly refer the note given after Clause 2.1.4.3 (2). Minimum 24 Nos of 15-minute time blocks are required to account the day for PR measurement. Otherwise the PR test shall be extended to another day.
104 | CUF | Pls confirm the percentage of CUF required | Technical | Kindly refer S.No.6 of Amendment-1.
105 | Irradiance variation will not be considered for the calculation of CUF. | GHI is not under control of contractor , we request SECI to provide GHI Correction factor with respect to Reference GHI and Actual GHI, or provide GHI Reference value.(SECI has already Considered GHI Correction for SECI-THDCIL 50 MW tender) | Technical | Terms & conditions of the original Tender document will prevail
106 | D + 9 months | We request SCCL to accept part commissioning also. | Technical | No part commissioning is allowed. Individual site with complete capacity can be commissioned.
107 | Adequate capacity of Solar PV Module | Kindly confirm if there is any specific AC/DC ratio | Technical | Kindly refer S.No.6 of Amendment-1.
108 | Arranging land Lease | We infer that the land is under the ownership of SCCL and will be provided along with Notice to proceed. | Technical | Land is under the owner ship of SCCL.
109 | 5.1.14 Laying of underground / over ground Cables (all types, as applicable) with proper arrangements along with appropriate sized ferrules, lugs, glands and terminal blocks. Laying of cables inside the building trench and other locations as required shall be over GI cable trays with proper support and accessories. | Cable tray may not be required for UG cables. | Technical | Terms & conditions of the original Tender document will prevail
110 | Project site distance | Please provide the distance between the two plots at Pedapally for proposed 50MW Plant. Also how the common evacuation shall be carried out from two different plots? | Technical | Bidder may visit site for due diligence.
111 | Auto cad of plots | Pls support by providing autocad layout of the plots along with boundary line co-ordinates for each plot. | Technical | Attached. However, it shall be noted that the given site layouts are indicative only.
112 | Approved makes | We request SECI to provide Approved makes, if any | Technical | Kindly refer S.No.5 of Amendment-1.
113 | E-RA on individual Site basis | Since , the package is different we request SCCL to award indivial sites to the bidders as selected through individual RA or to conduct RA for complete 150 MW Project. | Contractual | Bidders are required to refer Sr No 40, Amendment-1 for the same.
114 | Separate EMD and Tender processing fees | We infer that bidders has to submit single EMD and Tender processing fees | Contractual | Bidders are required to submit the Bid Processing Fee & EMD for the single 129 MW capacity basis as per the amount mentioned under the Tender and Sr No 41, Amendment 1
115 | The work execution planning for supply, erection, commissioning and all other allied works for SPV Power Plant shall be such that it is completed within stipulated time from the date of order/ LOI/ NTP. | Project should be completed within stipulated time from the date of order/ LOI/ NTP whichever is later., pls accept as the project site is divided on several parts. | Contractual | Bidders are required to refer Amendment-1
116 | First Contract and Second contract (O&M) | For better tax optimization we request SCCL to accept this clause : (i) First Contract (for Supply): FOR destination basis Supply of all Equipment and materials including mandatory spares and any other supplies specified in the Contract Documents. (ii) Second Contract (for Services) : For providing all services i.e. Transportation for delivery at site, Insurance, Unloading, Storage, Handling at Site, Civil Works, Erection, Installation, Testing and Commissioning including Performance Testing in respect of all the Equipment supplied under the "First Contract" and any other services specified in the Contract Documents. Both contracts will contain a cross fall breach clause specifying that breach of one will constitute breach of the other. (iii) Third Contract (for O&M): For providing Comprehensive operation & maintenance of the Solar PV plant for 10 (Ten) years from the date of Operational Acceptance, as detailed in technical specification including supply and storage of all spare parts, consumables, repairs/ replacement of any defective equipment etc. | Contractual | Bidders are to be apprised that the Project is not a stand alone Supply or Service or O&M contract. The activities/supplies of the Supply contract are mutually interdependent on the Service contract & Vice Versa. Both the contracts are mutually inclusive of each other and can't remain in isolation, as its a kind of EPC cum Works contract and not any stand alone contract. Its the sole responsibility of the Bidders to remain liable for all the supply, services, activities & plans during the entire terms of the contract. Hence, the Terms and conditions of the original tender document will prevail. Bidders are required to exercise their appropriate Due Diligence while submitting their respective Bid Prices considering the appropriate GST.
117 | Price part to be filled online and SOR 1 and SOR 2 to be uploaded | There seems to be discrepancy, pls confirm if price bid is only to be filled online or has to be uploaded. | Contractual | Bidders are required to fill the Revised SOR 1 & SOR 2 sheets for the detailed price Break up and upload the same while submitting their price Bids. This uploading of Excel sheets is called Main Bid. Secondly, bidders are also required to fill online the total summary of the price at TCIL as the "Electronic Form" Further, Bidders are required to Refer the Section II, Instruction to Bidders, Annexure II, Clause 5.3 stating : If any variation is noted between the price mentioned in the Electronic Form™ and the Main Bid (Refer Clause No. 5.2 B for the definitions of Electronic Form and Main Bid), the price mentioned in the Main Bid shall prevail.
118 | At the option of the Employer/ Owner, the work for which the Tender had been invited, may be awarded to one Contractor or split between more than one bidders, in which case the award will be made for only that part of the work, in respect of which the bid has been accepted. | Since the project is in different packages , we request SCCL/SECI to to award bidders as per the selection done individually during RA. Or to confirm if all the projects will be awarded to single bidder. | Contractual | Bidders are required to refer Sr No 40, Amendment-1 for the same.
119 | Further, contractor shall also facilitate owner in getting the required permissions/agreements as required for the energy accounting by State agencies/DISCOM. Bidders are advised to include any such costs in their final offer/Price BID. | We infer that that this project will be set up for captive Purpose. Kinley clarify what approvals are required to be taken by the contractor. | Technical | The plants are intended for captive usage but open access will be required for consumption of the generated energy at different SCCL locations. SCCL shall make the application for Open Access. However, the Contractor shall facilitate SCCL in obtaining the same.
120 | ROW | We request SCCL to take the scope of ROW in their scope. | Technical | ROW is in the scope of Contractor.
121 | Whenever a fault occurs, the Contractor has to attend to rectify the fault & the fault must be rectified within the 48 hours from the time of occurrence of fault. | Practically Few major repairs may not be possible for getting repaired within stipulated 48 Hours, Further, the contractor is already liable for loss of penalty for under generation, hence, this clause leads to double implication of penalty, we request the employer to remove this double LD for same event. | Contractual | Bidders are required to refer Sr No 43, Amendment-1 for the same.
122 | However, where value of BG is Rs.5 lakhs and above, the BG should be obtained from the bank branches situated at Hyderabad / Kothagudem or operative and payable at bank branches situated at Hyderabad/ Kothagudem. | This may not be possible for the contractor to get the BG issue from Branches of Hyderabad only, we request SCCL to accept BG from banks as mentioned in the tender from any branches. | Contractual | Terms & conditions of the original Tender document will prevail. Bidders are required to refer Clause No. 5 of SCC.
123 | CPBG 10 % And 5 % | As and industry Practice the CPBG for 5% should be on O&M Contract price and not on over all supply & Services. | Contractual | Terms & conditions of the original Tender document will prevail
124 | O & M Charges on YoY basis must be in equal or in ascending order only. | O&M Charges my differ on YoY, pls allow bidders to assume O&M value as per their discretion. | Contractual | Terms & conditions of the original Tender document will prevail
125 | The above warranties shall be backed by third party insurance. | Non of the Indian Module manufacturer has third party insurance , keeping this clause will lead to restrictive trade practice , we request SECI/SCCL to delete this clause and let Indian Module manufacturer to participate as well. | Technical | Terms & conditions of the original Tender document will prevail
126 | Action and compensation in case of bad works | This clause leads to interpretation of unauthentic penalty/compensation. The EIC should not be empowered with willingness to charge this compensation just by appreance of the work, hence, this may lead to contractual dispute, we request SCCL to delete this clause. | Contractual | Bidders are required to refer Sr No 45, Amendment-1 for the same.
127 | cutting of trees | We infer that the land is under the ownership of SCCL, hence, land should be provided after Cutting and felling of tress to the contractor for smooth execution of the project. | Technical | Uprooting of eucalyptus trees will be done by SCCL. Cutting of trees other than eucalyptus is in the scope of the Contractor.
128 | Approval for tree cutting | We infer that the land is under the ownership of SCCL, hence, approval for cutting of trees should be given by SCCL. | Technical | Uprooting of eucalyptus trees will be done by SCCL. Cutting of trees other than eucalyptus is in the scope of the Contractor.
129 | Value of the indemnity bond | We request you to provide value of indemnity bond | Finance | The indemnity Bond will cover the Total contractual value